## Risk Ranking
Team members: Bassam Hallani, Ray Marsh |  |  | Date created for this workplace: |  | Date of This Revision: 23/03/2022 | Workplace: 101-103 Miller Street | [5 empty] | Division: O&I Commercial
Current Revision:(A)
LIKELIHOOD (L) |  |  | CONSEQUENCE (C) - IMPACT |  |  | RISK RANKING (R) | [5 empty] | Risk Ranking Summary
[7 empty] | 1 | 2 | 3 | 4 | 5 | EXTREME-These risks are Unacceptable. The work activity should be halted until Critical Controls are implemented which reduce the risk to no greater than High. If it is not possible to reduce the risk, the work should remain prohibited.
A | Almost Certain | Expected to be the outcome in most cases - 91 - 100% probable | 1 | Insignificant | First aid injury/s (FAI), minor environmental impact. Minor/ medium term social impacts on local population, or expected financial impact = < $10k. | A | M (8) | M (13) | H (18) | E (23) | E (25)
B | Likely | Will probably occur in most circumstances - 51 - 90% probable | 2 | Minor | Medical Treatment Injury (MTI), minor short term environmental impact. Attention from media & heightened concern by local community or expected financial impact = $10k - $100k. | B | M (7) | M (12) | H (17) | H (21) | E (24) | HIGH-These risks must be reduced where possible by implementing higher levels of Critical Control using the Hierarchy of Controls. Where the residual risk is not able to be reduced lower than High, a controlled work methodology must be in place and reviewed by the HSE Lead and Workplace Manager.
C | Possible | Might occur some time 31 - 50% probable | 3 | Moderate | Lost Time Injury (LTI). Serious irreversible injury/disease, serious medium term environmental harm. Adverse local media coverage, or expected financial impact = $100k - $1 mill. | C | L (4) | M (11) | H (16) | H (20) | H (22) | MEDIUM-Identified Critical Controls must be capable of reducing the risk by eliminating or minimising to an acceptable level. # Critical Activities & Monitoring are to be identified and implemented by Supervisory staff.
D | Unlikely | Could occur, but would not be expected - 10 - 30% probable | 4 | Major | Single fatality, permanent localised environmental harm. Substantial risk to corporate reputation, sustained adverse local media coverage, major repairs or project outcomes affected, or expected financial impact = $1 - 10 mill. | D | L (3) | M (6) | M (10) | H (15) | H (19) | LOW-The work is relatively safe and can be managed by following routine MMRs, procedures, guidelines & JSEA/SWMS. No further action is required, unless additional hazards arise during the work.
E | Rare | Rare that this would occur - no previous occurrence in similar circumstances - < 10% probable | 5 | Catastrophic | Multiple fatalities, permanent long term and extensive environmental harm. Extreme risk to corporate reputation, public outrage & national media coverage, high profile litigation, class action, threat to business division viability or expected financial outcome = $10 - $100 mill. | E | L (1) | L (2) | L (5) | M (9) | H (14) | HIERARCHY OF CONTROLS Eliminate - remove hazard completely; Substitute - replace with less hazardous; Isolate - separate the worker from the hazard Engineer - guarding, mechanical aids, ventilation; Administrate - reduce exposure, procedures, consultation; PPE - to be used in addition to above.
Mirvac HSE
Element 3 - Risk Management
Risk & Opportunity Register
Mirvac HSE
Element 3 - Risk Management
Risk & Opportunity Register

## Typical Hazards & Aspects
Typical Significant Hazards & Aspects Checklist
CONTACT WITH ELECTRICITY - Any contact with electricity by person or by plant /vehicle leading to potential electric shock to a person. | HOT WORK - Any Flame or Spark producing activity - welding, gas-cutting, grinding which may cause fire or injury. |  | EFFECTS ON COMMUNITY - Any activities that may lead to actual or percieved degradation of the local community environment e.g. heavy traffic, parking, noise or negative interaction with project personnel.
FALLING OBJECTS - Potential for objects, tools, materials to fall to levels below and cause injury or damage. | MANUAL HANDLING - Stress to muscles from repetitive movements, sudden loading, incorrect lifting, handling techniques or overloading. |  | DISTURBANCE TO FLORA & FAUNA - Disruption, damage or injury to animals, their habitat or local trees, vegetation and plants.
MOVING PLANT/ VEHICLES - Potential collision between items of moving plant/ machinery, or vehicles or contact with persons | CABLES UNDER TENSION - Pre & Post Stressing of concrete. Come-along or chain-block use, hoists and slings. |  | VIBRATION - Vibration from activities that may have a physical effect on the surrounding environment.
MOVING PARTS & STORED ENERGY - Person hit by suspended / flying object, contact with or entanglement in moving parts. | STRUCTURAL FAILURE - Falsework, Formwork & Masonry walls. Collapse or loss of the load-carrying capacity of a component or the structure itself. | SOIL EROSION & SURFACE RUN-OFF - Loss of ground material due to wind/ water action, causing potential siltation/ pollution of waterways. | ENDANGERED SPECIES - Incorrect management, habitat control & identification of endangered species in the local environment.
SUBSTANCES INCLUDING CHEMICALS, GASES & DANGEROUS GOODS - Potential contact to eyes, skin or lungs with Hazardous Substances or Dangerous Goods. | EXCAVATION/ PILING/ BORING/ TRENCHING - Fall of material causing engulfment, persons falling, plant overturning, flooding, contact with underground services. | CONTAMINATED / ACID SULFATE SOIL - Incorrect management/ identification of contaminated or ASS soils. | HERITAGE ISSUES - Incorrect management, consultation or identification of local cultural or heritage issues.
HAZARDOUS MATERIALS - Asbestos, Lead, Polychlorinated Biphenyls (PCBs), synthetic mineral fibres or other as identified causing significant illness. | WORK IN CONFINED SPACES - Areas identified as having potential atmospheric contamination, lack or excess of oxygen or engulfment by free-flowing solids or liquids. | SPILLS OR DISCHARGE CAUSING CONTAMINATION - Discharge & transfer of fuels/oils (hydrocarbons), hazardous substances, dangerous goods, concrete truck wash-out. | DEVELOPMENT APPLICATION REQUIREMENTS - Failure to properly evaluate and implement critical controls may lead to environmental harm, non-conformance, fines and damage to Mirvac reputation.
OCCUPATIONAL NOISE - Workplace noise levels from activities, plant or equipment which has the potential to cause hearing damage to persons in the vicinity. | WORK AT HEIGHT - Potential for persons to fall from an elevated postion and sustain a significant injury. | AIR QUALITY - Potential for pollution by dust, from wind action, disturbance of soil by vehicle/ plant movements. Exhaust emissions from plant/vehicles.
PROJECTILE FIRING TOOLS - Hilti or Ramset explosive charge tools and air or gas powered Nail guns. | WORK OVER OR NEAR WATER - Potential for persons/ plant to slip/ fall into water and risk of drowning. | WASTE - Incorrect management of solid/ liquid waste streams leading to contamination of the environment e.g. bulk earthworks, dewatering, concrete & paint.

## Risk & Opportunity Register
RISK & OPPORTUNITY REGISTER
Risk Ranking - Insert the "Untreated Risk" from the "Hazard / Aspect Worksheet" and then, according to the "Critical Controls" listed, and using the Risk Ranking matrix (Section 1) assess the "Treated Risk Ranking" appropriate to each row.
Appropriate R & O Register Hazards/Aspects and Critical Controls to be included in all workplace activity JSEAs (or equivalent)
Element | Risk | Untreated Risk | Critical Controls | Hierarchy of Controls | Critical Activities | Monitoring Activities | Treated Risk | Responsible | Legal and Other Requirements
ACCESS & EGRESS
Fire & Emergency egress | Confusion Lack of control Trips and Falls Fatalities | H17 | • At the time of design and construction the property complied with relevant AS, BCA or construction guidance - (Ordinance 70 if prior to AS). • All Emergency access & egress points must be clear of obstructions at all times. • All emergency and exit lighting is operational. • Regular Tests and Evacuation drills are conducted. | Engineering | • Fire audit to confirm compliance. • Workplace Inspections undertaken according to Mirvac schedules. • Emergency lighting maintenance undertaken as per WRMP. • Contracts established to undertake fire drills and inspections to meet regulations. | Records of: • Fire audits and Compliance certificates. - (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Essential Services\Base Building Certificates) (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Contracts & Services\Fire Protection\Reports & Minutes\Test Results) • Workplace inspections. (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Daily Site & Fire Stairs inspection\2020) + Monthly FCR36 • Evacuation drills, current evacuation diagrams and signage. (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Contracts & Services\Emergency Procedures\Training Program) • Evaluation of evacuation. | M6 | Asset Manager, Facility Managent team, Service Providers | WHS Act 2011 Part 2 Health & Safety Duties WHS Regs 2011 The Building Code of Australia (BCA) The Disability Discrimination Act (DDA) AS/NZS2293.1:1998 : Emergency evacuation lighting for buildings - System design, installation and operation. AS 1851-2012 : Routine service of fire protection systems and equipment | Occupational Health & Safety Act 2004: - 21. Duties of employers to employees - 23. Duties of employers to other persons - 26. Duties of persons who manage or control workplaces Occupational Health & Safety Regulations 2007. The Building Code of Australia (BCA) The Disability Discrimination Act (DDA) AS/NZS2293.1:1998 : Emergency evacuation lighting for buildings - System design, installation and operation. AS 1851-2012 : Routine service of fire protection systems and equipment
Public access around hazardous activities | Public exposure to hazardous activities | M12 | • Service Provider & maintenance to erect adequate barricades/ hoardings/ signage in accordance with agreed JSEA/SWMS. • Inductions to cover Mirvac's requirements. | Isolation | • Mirvac staff aware of all activities in public areas, • JSEA/SWMS checked by facility managemnt team to ensure they are suitable for the designated area. | • Regular workplace inspections. (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Daily Site & Fire Stairs inspection\2020) + Monthly FCR36 | M6 | Asset Manager, Facility Managent team, Service Providers
Safe access though public areas/common areas | Slips, trips & falls | H16 | • Floors to be designed to have complaint slip ratings, non compliant surfaces to be identifed and managed accordingly. • Quick response to incliment weather or spills. | Administration | • Annual slip testing to take place • Workplace Inspections undertaken according to the WRMP and service provider cleaning agreement. | • Workplace Inspections undertaken according to the WRMP and service provider cleaning agreement. • Discuss and advise tenants to assist in ensuring floors are free from risk where possible. Salesforce reporting procedure • Cleaning rotation inspections as per SLA. • Records of Workplace inspections. (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Daily Site & Fire Stairs inspection\2020) + Monthly FCR36 | M6 | Asset Manager, Facility Managent team, Service Providers
AIR QUALITY
Indoor and outdoor air quality | Adverse reactions to chemicals, particles and/or substances in the air | H16 | • Provide clean, healthy, fresh air to facility at all times. • Ensure adequate ventilation. • Ensure recommended chemicals and treatments are used in the correct quantities at all times. • Plant, equipment and filters areinspected and cleaned on a regular basis. • All chemcials to be used in accordance with the Safety Data Sheet (SDS). | Engineering | • Anual air quality testing for bacteria, CO’s, temp and humidity, or at more frequent intervals if deemed necessary. • Corrective and preventative actions implemented and recorded for any out of parameter levels. | • Monthly testing of water system quality. H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Cooling Towers\Test Results\2020 (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\HSE\5.0 Measurement and Evaluation\Indoor Air Quality Reports) • Service Provider to be regularly monitored to ensure inspections are completed as per the SLA. (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Daily Site & Fire Stairs inspection\2020) + Monthly FCR36 | M6 | Asset Manager, Facility Managent team, Service Providers | Safe Work Australia – National Code of Practice for the Safe Use of Synthetic Mineral Fibres NOHSC:2006(1990)] Refer cell I 261 for environmental - related Legislation, Standards, Codes Plant Equipment & Tools MMR; Occupational Exposures MMR;
BIOLOGICAL
Infection control | Exposure to blood borne infectious diseases | H16 | • Ensure blood/faeces are cleaned up immediately after reporting, ensuring cleaners adherence to their own company procedures. • Ensure hypodermic needles, syringes, condoms or other, are collected immediately after they are reported utilising the recommended containers and tools as per SWMS / JSEA. | Elimination | • Provide appropiate training, equipment and PPE for managing biological hazards. • Dispose of biological waste in accordance with SWMS / JSEA. | • Service Provider to be regularly monitored to ensure activities are completed as per the SLA. (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Daily Site & Fire Stairs inspection\2020) + Monthly FCR36 | L3 | Asset Manager, Facility Managent team, Service Providers | WHS Regulation 2011 (s)42 First Aid AS4031 Non-reusable containers for the collection of sharp medical items used in health care areas. National Code of Practice: Control of Work Related Exposure to Hepatitis and HIV (blood-borne) Viruses [NOHSC: 2010 (2003)]
COMMUNITY CONTACT
Community contact | Public safety Brand reputation Adverse media coverage | M10 | • All contact from the community including complaints, reports etc. are to be registered in iSystain within 24 hours • All media enquiries to be directly managed by the Mirvac Commuications Team. | Administration | • Respond to complaintnat within 48 hrs. | • Records maintained in iSystain. | L3 | Asset Manager, Facility Managent team, Service Providers | Environmental Planning & Assessment Act Mirvac Group form Community Contact Notification
CONTACT WITH ELECTRICITY
Electrical tools & equipment | Electrocution or fire | H22 | • Industrial rated tools and equipment only including leads and plugs. • Elevation of leads and protection with plastic stand hooks; • Use of portabel RCDs as required. • Ensure all electrical equipment is used and maintained as per manufactures recommendations and operational manuals. | Engineering | • Pre-start check of condition of leads and tools and check within test date; • Lock out/tag out all faulty equipment. • Ensure all equipment is currently tagged and tested. | • Electrical tag and testing records H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\HSE\5.0 Measurement and Evaluation\Electrical\Test & Tag | M10 | Asset Manager, Facility Managent team, Service Providers | NSW: Work Health and Safety Act 2011 (NSW) Work Health and Safety Regulation 2017 (NSW) Electrical Supply Act 1995 (NSW) Electricity Supply (General) Regulation 2014 Electricity Supply (Safety and Network Management) Regulation 2014 Vic: Occupational Health and Safety Act 2004 (Vic) Occupational Health and Safety Regulations 2017 (Vic) Electricity Safety Act 1998 (Vic) Electricity Safety (Installations) Regulations 2009 (Vic) Qld: Work Health and Safety Act 2011 (Qld) Work Health and Safety Regulation 2011 (Qld) Electrical Safety Act 2002 (Qld) Electrical Safety Regulation 2013 (Qld) ACT: Work Health and Safety Act 2011 (ACT) Work Health and Safety Regulation 2011 (ACT) Electricity Safety Act 1971 (ACT) Electricity Safety Regulations 2004 (ACT) WA: Occupational Safety and Health Act 1984 (WA) Occupational Safety and Health Regulations 1996 (WA) Electricity Act 1945 (WA) Electricity Regulations 1947 (WA) Electricity (Licensing) Regulations 1991 (WA) AS/NZS 3760 In-service safety inspection and testing of electrical equipment AS/NZS 3012 Electrical Installations – Construction and demolition sites AS/NZS 3190 Approval and test specification - Residual current devices (current-operated earth-leakage devices) AS/NZS 3199 Approval and test specification - Cord extension sets AS/NZS 3008.1.1 Electrical installations - Selection of cables for alternating voltages up to and including 0.6/1 kV - Typical Australian installation conditions Work with Electricity MMR Plant Tools and Equipment MMR | AS/NZS 3010 - Electrical installations - Generating sets AS/NZS 3017 Electrical installations - Verification guidelines AS/NZS 3001 Electrical installations - Transportable structures and vehicles including their site supplies AS/NZS 3000:Electrical installations (Australian/New Zealand Wiring Rules) AS/NZS 4836 Safe working on low voltage installations Safe Work Australia - Managing electrical risks at the workplace: Code of Practice Work Cover NSW – Electrical Practices – Construction and Demolition Sites: Fact Sheet (website current) Work Cover NSW - Managing electrical risks in the workplace: Code of Practice Work Safe QLD - Electrical Safety - Works: Code of Practice Work Safe QLD - Electrical safety - Managing electrical risks in the workplace: Code of Practice Work Safe QLD - Managing electrical risks in the workplace: Code of Practice Work Safe Vic –Electrical installations on construction sites: Industry Standard Work Safe WA - Safe Low Voltage Work Practices by Electricians: Code of Practice Work Safe WA - Guidelines for the Safe management of high voltage electrical installations Energy Safety Division WA - WA Electrical Requirements (WAER) ; AS/NZS 3760 In-service safety inspection and testing of electrical equipment AS/NZS 3012 Electrical Installations – Construction and demolition sites AS/NZS 3190 Approval and test specification - Residual current devices (current-operated earth-leakage devices) AS/NZS 3199 Approval and test specification - Cord extension sets AS/NZS 3008.1.1 Electrical installations - Selection of cables for alternating voltages up to and including 0.6/1 kV - Typical Australian installation conditions AS/NZS 3010 - Electrical installations - Generating sets AS/NZS 3017 Electrical installations - Verification guidelines AS/NZS 3001 Electrical installations - Transportable structures and vehicles including their site supplies AS/NZS 3000:Electrical installations (Australian/New Zealand Wiring Rules) AS/NZS 4836 Safe working on low voltage installations Safe Work Australia - Managing electrical risks at the workplace: Code of Practice Work Cover NSW – Electrical Practices – Construction and Demolition Sites: Fact Sheet (website current) Work Cover NSW - Managing electrical risks in the workplace: Code of Practice Work Safe QLD - Electrical Safety - Works: Code of Practice Work Safe QLD - Electrical safety - Managing electrical risks in the workplace: Code of Practice Work Safe QLD - Managing electrical risks in the workplace: Code of Practice Work Safe Vic –Electrical installations on construction sites: Industry Standard Work Safe WA - Safe Low Voltage Work Practices by Electricians: Code of Practice Work Safe WA - Guidelines for the Safe management of high voltage electrical installations Energy Safety Division WA - WA Electrical Requirements (WAER)
Undertaking Electrical Work on or near energised services (installation, commissioning, maintaining, fault finding, isolating, testing, re-energising) | Electrocution Explosion | H22 | • Person not working on 'live' equipment (e.g., Distribution Board or circuit isolated & locked out); • Hard barriers to maintain safe approach distances and prevent inadvertent contact; • Rated insulation/intrinsically safe tools to protect if contact occurs; • Isolation Lockout Tagout MMR and personal locks; • Earth leakage protectors and inbuilt fault tripping; • Isolation Lockout Tagout Permit; • Training and Competency; • Emergency Recue Kits and Standby Person; • Electrically rated PPE, mats, gloves, multimeter; • Electrical Handover processes and certificate. | Engineering | • Person is licenced electrician using Service • Provider Isolation Procedure or trained in Mirvac Isolation Procedure | • Record of competency & isolation training provided H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\HSE\4.0 Implementation\4.6 Hazard notification reports\4.6.2 Permits to work\All Permits • Physical lock out/isolation system observed in operation • Register of lock out/isolation system implementation | H19 | Asset Manager, Facility Managent team, Service Providers | Refer Legislation, Codes and Standards in cells I 8-9, I 15 and I 16. WHS Regs 2011 section 291 (k) WHS Regs 2011 Part 4.5, section 81 - 112, High Risk Work AS 3000:2007 - Electrical Installation (Wiring Rules) cl 2.3; AS 1892.5:2000 - Portable Ladders - Selection, Safe Use and Care - cl 3.1; AS/NZS 3760 In-service safety inspection and testing of electrical equipment AS/NZS 3012 Electrical Installations – Construction and demolition sites AS/NZS 3190 Approval and test specification - Residual current devices (current-operated earth-leakage devices) AS/NZS 3199 Approval and test specification - Cord extension sets AS/NZS 3008.1.1 Electrical installations - Selection of cables for alternating voltages up to and including 0.6/1 kV - Typical Australian installation conditions AS/NZS 3010 - Electrical installations - Generating sets AS/NZS 3017 Electrical installations - Verification guidelines AS/NZS 3001 Electrical installations - Transportable structures and vehicles including their site supplies AS/NZS 3000:Electrical installations (Australian/New Zealand Wiring Rules) AS/NZS 4836 Safe working on low voltage installations; Isolation Lockout Tagout MMR; Work with Electricity MMR.
CONFINED SPACES
• Grease traps (Located B6 loading dock) • Pits (14 x Lift Shafts 2 x sump pumps) • water Tanks (3 x tanks) • Cooling towers (101 Miller St. 5 x CT L35 & 103 Miller St. 1 x CT L3) | Entry by unauthorised person | H20 | • Design out and eliminate the need to enter confined spaces where possible; • Confined spaces labelled and access restricted (e.g. Key locked, signage, barricade) (isolation); • Maintain a register and risk assessment for Confined Spaces (administrative) • Confined space entry controlled through permitting system (administrative);Design out confined spaces where possible; | Isolation | • Confined space entry permit completed by person trained in confined spaces (by RTO with confined spaces in their scope). • Entry restricted to persons with confined space training certificate. • Person that accepts risk assessment is trained in risk assessment • Standby person at confined space entry point controls entry and exit • Gas monitor has a current calibration and is 'bump tested' in fresh air prior to each use. • Emergency retrieval system has been prepared or authorised by a person that is confined space trained (by RTO with confined spaces in their scope). | • Register of Identified Confined Spaces and risk assessment. • Record of training • Register of persons entry/exit to space Confined Space Permit to be filled prior accessing | H15 | Asset Manager, Facility Managent team, Service Providers | AS/NZS 2865:2009 Safe Working in a Confined Space - s11; WHS Reg 2011 section 291 (f) WHS Regs 2011 Part 4.3, sections 62 - 77, Confined Spaces, WHS Regs 2011 Part 4.5, section 81 - 112, High Risk Work WHS Code of Practice - Confined Spaces Confined Space Entry MMR
CONSTRUCTION ACTIVITIES
Principal Contractor construction activities | Injuries to people, damage to property and the environment | H16 | All construction works over $250,000 ($350,000 VIC) performed on site must have an appointed Principal contractor. All construction works below this amount must have a licensed builder. Principals Contractors must be appointed in accordance with the Mirvac Principal Contractor Managment Procedure. Mirvac Contractor Registration & Qualification Process to be undertaken by Principal Contractor in consultation with HSE. Contractors to follow and abide by their own SWMS/JSEA for specific work being undertaken. | Administration | A representative from the PC is to undertake the Mirvac Contractor Registration and Induction process. All employees and subcontractors of the PC must undertake the PC's induction for the project. If a PC is not required to be appointed, all contractors must follow the Mirvac Contractors Registration and Induction process. A representative from the PC is to log in/ out of contractor management system (CMS) daily whilst works are being undertaken. PC employees and subcontractors conducting building impact works must sign in/out of the CMS terminal. | BM to conduct periodical inspections of construction as per FCR37. Implementation Review to be undertaken by HSE. | M10 | Asset Manager, Facility Managent team, Service Providers, HSE | WHS Regulation 2011 Chapter 6 Construction Work Occupational Health & Safety Act 2004 (VIC) Occupational Health & Safety Regulations 2007 – Chapter 5 – Part 5.1 (VIC) Occupational Safety and Health Act 1984 (WA) Occupational Safety and Health Regulations 1996 Division 11, 12 (WA) Mirvac Standard Terms & Conditions Mirvac Step by Step Guide to Registration & Qualification O&I Service Provider Management Procedure Mirvac Principal Contractor Management Procedure
Construction activities Refurbishments/Refit etc. | Injuries to people, damage to property and the environment | H16 | All construction works under $250,000 ($350,000 VIC) must be completed by a licensed contractor. Mirvac Contractor Registration & Qualification Process to be undertaken by Mirvac contractors and tenant contractors undertaking building impact works. Contractors to follow and abide by their own SWMS/JSEA for specific work being undertaken. | Administration | Contractors to log in/ out of contractor management system (CMS) daily whilst works are being undertaken. BM to review CMS for site access and compliance. | All contractors and tenant contractors conducting building impact works must complete Mirvac registration and induction process prior to starting works. BM to conduct periodical inspections of construction as per FCR37 | M10 | Asset Manager, Facility Managent team, Service Providers
CONTRACTOR MANAGEMENT
Mirvac and Tenant Contractors | Injuries to people, damage to property and the environment | H17 | • Mirvac Contractor Registration & Qualification Process to be undertaken by contractor. • Contractor audit FCR37 to be conducted twice a month. • Review SWMS to ensure adequate control are identified in SWMS. • Contractor to follow Mirvac HSE Management System | Administration | • Contractors to log in/ out of contractor management system (CMS) daily whilst works are being undertaken. • FM to review CMS for site access and compliance | • Completion of Mirvac General and Workplace Specific inductions prior to attending site. • FCR 37 • HSE Observations | M10 | Asset Manager, Facility Managent team, Service Providers | WHS Regulation 2011 – Chapter 6 Construction Work Mirvac Standard Terms & Conditions Office & Industrial Service Provider Management Procedure
EMERGENCY PREPAREDNESS
First aid Located at security office, Centre management, Concierge desk, and plant room entries Defibrillator located at Security office | Injuries to people, damage to property and the environment, including escalation | M11 | • First aid officer to undertake competency-based training form a RTO. • A first aid officer to be on shift at all times. • First Aid Officer poster to be displayed in all visible locations. | Administration | • Site Specific Procedures Manual to be held on site. • BM to ensure evacuation plans (with identified “you are here” stickers) are in place and displayed at Mirvac Retail workplaces. | • Observe that evacuation plans are in place and displayed in prominent locations. (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Contracts & Services\Emergency Procedures\You Are Here Posters) • Regular evacuation training is provided to tenant employees including first aid (supplies and training). (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Contracts & Services\Emergency Procedures\Training Program) | L2 | Asset Manager, Facility Managent team, Service Providers | WHS Act 2011 (s)20 Further duties of PCBU WHS Regulation 2011 (s) 42-43 First Aid & Emergency Plans WHS Regulation 2011 (s) 39 & 43 General Workplace Management AS3745 Planning for Emergencies in Facilities AS1851 Routine service of fire protection systems and equipment AS1319 Safety signs for the occupational environment
Naturals disasters | Loss of life, property and interruption to business operations | H22 | • Senior management to be involved to review the location (proximity to hazard – flood prone areas/bush fire zones) and type of asset (structure - to determine if the risks to the asset can be eliminated or minimised. • Flood prevention and mitigation strategies to be developed in line with local government recommendations. All new builds and refurbishments are to undergo the DOOR process to ensure Flood/Bushfire risk may be reduced by the design. | Administration | • Where the risk is present as determine by the DA or council requirements, the development of a flood/bushfire management plan linked to the Emergency Response/business continuity plan (BCP) is to completed and implemented (communicated) into the facility overall site specific procedures. | • Weather events which have the likelihood to impact the property are to be monitored through local and state media (bureau of Meteorology, News (TV/Radio) stations. | L3 | Asset Manager, Facility Managent team, Service Providers
Evacuation/Bomb Threats | Damage to Property | H22 | • Evacuation and control procedures documented by Mirvac Retail specific emergency evacuation consultant. Documents to be held on site by site team. • Procedures to be practiced regularly. • Document to be reviewed on a regular basis. | Administration | • Where the risk is present as determine by the DA or council requirements, the development of a flood/bushfire management plan linked to the Emergency Response/business continuity plan (BCP) is to completed and implemented (communicated) into the facility overall site specific procedures. | • Weather events which have the likelihood to impact the property are to be monitored through local and state media (bureau of Meteorology, News (TV/Radio) stations. | M9 | Asset Manager, Facility Managent team, Service Providers
Fire | Fire, loss of life and property | H15 | • All buildings to include fire protection systems to detect and prevent the spread of fire. • Fire systems to be identified in Emergency & Evacuation Management Plans • All isolations of fire systems to be recorded by “Isolation Permit” at Building Management as well as isolation log book at FIP. | Administration | • Verification of annual Maintenance requirement – Service Providers to comply with AS1851 (Routine service of fire protection systems and equipment) • Emergency Evacuation training for all employees and use of certain fire equipment (QLD/ fire extinguisher). • All systems and equipment to be tested as per AS 1851 and certified by contractor allow the Annual Fire Safety • Statement to be completed and issued to council, as well as Insurers and National Ops Mgr. advised of impairments and of their return to service. | • Fire system inspection and critical dates maintained as per Mex requirements. (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Contracts & Services\Fire Protection\Service Dockets\Fire Alarm Panel Tests) • Annual Emergency Evacuation Drills H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Contracts & Services\Emergency Procedures\Training Program • Bi- Annual Emergency Control Organisation (ECO) training. | L5 | Asset Manager, Facility Managent team, Service Providers
ESCALATORS, TRAVELATORS AND LIFTS
Lifts | Entrapment, falls from heights, crush injuries | H20 | • Lifts operation and maintenance must be in compliance to Mirvac Retail Lifts, Escalator and Travelators Procedure. • Regular inspections to be undertaken. | Isolation | • Lifts are to be covered by comprehensive (maintenance) contracts provided by recognised lift maintenance companies. | • FM to carry out routine inspections of lifts as per FCR36 requirements. (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Daily Site & Fire Stairs inspection\2020) + Monthly FCR36 | M9 | Asset Manager, Facility Managent team, Service Providers | NSW: Work Health and Safety Act 2011 (NSW) Work Health and Safety Regulation 2017 (NSW) Qld: Work Health and Safety Act 2011 (Qld) Work Health and Safety Regulation 2011 (Qld) ACT: Work Health and Safety Act 2011 (ACT) Work Health and Safety Regulation 2011 (ACT) WHS Act 2011 (s)20 Further duties of PCBU WHS ACT 2011 – (s)21 - Duties of PCBU involving management or control of fixtures, fittings or plant at workplaces AS/NZS 1735 Lifts, escalators and moving walkways
FALLING OBJECTS
Stationary Working Platforms (e.g., scaffolds, elevated walkways, trestles) including collapse | Object falling from hight Hit / Strike employee or member of public | H16 | • Use of physical barriers to prevent objects dropping (containment meshing); • Brick guards fitted where potential for falling objects exists; • Protection of the structure from being hit by loads or mobile plant; • Toe boards installed; • Scaffolds, walkways, elevated work areas e.g., slabs, roofs have toe boards installed.; • Work within the design rating of the equipment; • Management of Change process to ensure integrity is maintained when structure changes; • Scaffolding design drawings and plans and checks that construction is compliant. | Isolation | • Handover certificate received • Mirvac inspection prior to acceptance. | • Records of Certificates and Inspections • On-site observation | M10 | Asset Manager, Facility Managent team, Service Providers | WHS Regs 2011 section 291 (o) WHS Regs 2011 section 54 - 55, Falling Objects AS 2550.10-2006 Cranes, Hoists & Winches - Mobile Elevated Work Platforms - cl 4.3; AS 1800 - Occupational Protective Helmets Selection, Care and Use - cl 2.2, s 3; Work at Height MMR and Reference Document Plant Equipment & Tools MMR (refer Legislation, Codes and Standards)
Mobile Working Platforms (e.g. Elevated Work Platform (EWP), Scissor Lift, Swinging Stages, mobile scaffolds) | Object falling from hight Hit / Strike employee or member of public | H16 | • Staging of the work when no one else around; • Separated work fronts to avoid simultaneous operations; • Adhere to minimum standards for design compliance; • Exclusion zone implemented • Work within the design rating of the equipment; • Management of Change process to ensure integrity is maintained when structure changes; • OEM requirements complied with; • Processes for the management of Design of Temporary Works; • Plant Arrival Checklist; • Plant Risk Assessment; • Plant maintenance and inspection regime; • Verification of Competency for operators; • High Risk Work Licenses where required (e.g. scissor lift over 11m). | Elimination | • Handover certificate received • Mirvac inspection prior to acceptance • Exclusion zone marked and maintained | • Records of Certificates and Inspections H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\HSE\4.0 Implementation\4.6 Hazard notification reports\4.6.2 Permits to work\All Permits • On-site observation | M10 | Asset Manager, Facility Managent team, Service Providers | WHS Regs 2011 section 291 (o) WHS Regs 2011 section 54 - 55, Falling Objects AS 2550.10-2006 Cranes, Hoists & Winches - Mobile Elevated Work Platforms - cl 4.3; AS 1800 - Occupational Protective Helmets Selection, Care and Use - cl 2.2, s 3; Work at Height MMR and Reference Document Plant Equipment & Tools MMR (refer Legislation, Codes and Standards)
HAZARDOUS SUBSTANCES
Storage and Handling of Hazardous Substances | Spills or discharge causing contamination Injury/Illness of Member of Public, Contractor or Worker | M10 | • Substances/goods stored and handled in accordance with SDS (Safety Data Sheet). • Appropriate bunding for hazardous chemicals with a minimuum of 110% capacity. • Untrained people not to use or determine storage requirements for hazardous substances or dangerous goods • Products stored in approved cabinets or purpose-built containment areas • Hazardous Substance Risk Assessment completed including research and purchase of less hazardous/ dangerous products • All users of hazardous substances appropriately trained and have adequate PPE • Spills kits in stock • Appropriate First Aid facilities including eye wash stations | Substitute | • Products & Hazardous Substances Register completed listed • SDS (Safety Data Sheet) for all products in use, issue date less than 5 years old. • Hazardous Substance Risk Assessment completed for all products/substances/goods classified as hazardous • Products/substances labelled • Person trained in storage and use of hazardous substance and dangerous goods as outlined on the HSRA and in the MSDS (SDS) • Appropriate number of spill kit and in appropriate locations | • Records of MSDS (SDS) H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\HSE\4.0 Implementation\4.6 Hazard notification reports\4.6.6.7 Material Safety Data Sheets\MSDS and SDS Details • Spill Kit stocked and audited. Located at B6 opposite to security office / and inside cleaners room at lobby ground level • Records of spill response training available. • On-site observation. • Drainage outlet to bunding locked. | L5 | Asset Manager, Facility Managent team, Service Providers | WHS Regs 2011 Section 341 - 346, Labelling and SDS WHS Code of Practice - Labelling of Workplace Hazardous Chemicals AS 1336:1997 - Recommended Practices for Occupational Eye Protection; AS 4501.2:2006 - Occupational Protective Clothing - General Requirements; AS 1715:2009 - Selection, Use and Maintenance of Respiratory Protective Equipment; AS 2161.1:2000 - Occupational Protective Gloves - Selection, Safe Use and Maintenance - Appendix A; National Code of Practice for the Control of Workplace Hazardous Substances [NOHSC:2007(1994)] National Code of Practice - Labelling of Workplace Substances [NOHSC:2012] WorkSafe ACT - Work Health and Safety (Labelling of Workplace Hazardous Chemicals: Code of Practice) Approval; Safe Work Australia - NOHSC: National Code of Practice for the Labelling of Workplace Substances - [NOHSC: 2012]. Safe Work Australia - National Standard - Storage and Handling of Workplace Dangerous Goods - [NOHSC: 1015] Safe Work Australia - Guidance Note - Placarding Stores for Dangerous Goods & Specified Hazardous Substances - [NOSHC:3009] Safe Work Australia - National Model Regulation for the Control of Workplace Hazardous Substances - [NOHSC:1005]
HAZARDOUS MATERIALS
Asbestos, Lead, Polychlorinated Biphenyls (PCBs), synthetic mineral fibres, lead or other as identified (also refer Asbestos in Occupational Exposures Section) 22,000L Diesel Generator fuel tank located B1 underground | Asthma, skin rashes, allergic reactions, allergic sensitisation, cancer, and other long term diseases from exposure to substances. Contamination through loss of diesel fuel to ground water | H22 | • Hazardous material survey to be conducted on all assets built before 2003 and if materials found a new survey to be completed every 5 years. • All identified asbestos must be labelled with the type and nature of the material (friable/non-friable). • Removal of asbestos to be conducted by licensed removalist. • Hazardous material to be disposed of in accordance with Local, State and Federal Legislation. • If suspected asbestos is found in asset it is to be treated as Asbestos; • Asbestos is to be wet down, National HSE Manager be notified, tests to be completed to determine if it is Asbestos. Current drawings of the UPSS and site plans A copy of the specifications and/or industry standards used in the design and construction of the UPSS Leak monitoring Emergency contacts Site access details & contacts | Administration | • Hazardous Material Survey to be reviewed prior to any work commencing • Contractor licensed by Environmental Regulatory Authority (ERA) • Transporter and receiver of waste are ERA Licensed • Waste transport certificate is obtained. • Signage and emergency response equipment available relevant to the class of substance/good stored. Fuel loss monitoring procedure: • Tanks are dip tested at each monthly maintenance and recorded on the service report • Fuel gauge is read and recorded monthly • Fuel Test – 6 Monthly • Leak Detection – 3 Monthly • Tank Integrity Test - Annual | • Records of survey/ licenses • Hazardous Materials - 5 yearly inspection of areas containing Asbestos by a competent person. • A Register of all Hazardous Materials to be kept on site. •Tanks are dip tested at each monthly maintenance and recorded on the service report •Fuel gauge is read and recorded monthly •Fuel Test – 6 Monthly •Leak Detection – 3 Monthly •Tank Integrity Test - Annual | H14 | Asset Manager, Facility Managent team, Service Providers | Safe Work Australia - Code of Practice for the Management and Control of Asbestos in Workplaces [NOHSC: 2018 (2005)] Safe Work Australia - Safe Removal of Asbestos 2nd Edition [NOHSC: 2002 (2005)] Safe Work Australia - NOHSC- Code of practice for the management and control of Asbestos in workplaces Safe Work Australia - Work Health and Safety (How to Safely Remove Asbestos) Code of Practice Safe Work Australia - Work Health and Safety (How to Manage and Control Asbestos in the Workplace) Code of Practice 2015 Work Safer NSW - How to manage and control asbestos in the workplace: Code of Practice Work Safe NSW - How to safely remove asbestos: Code of Practice Work Safe Qld - How to manage and control asbestos in the workplace - Code of Practice Work Safe Qld – How to safely remove asbestos Code of practice Work Safe Vic – Asbestos Contaminated Soil – Guidance Note Work Safe Vic – Managing Asbestos in Workplaces - Compliance Code Work Safe Vic – Removing asbestos in workplaces - Compliance Code Work Safe Vic – Asbestos Contaminated Soil – Guidance Note Australian Standard 4964 Method for the qualitative identification of asbestos in bulk samples Occupational Exposures MMR Australian Standard UPSS 4897-2008 R2016
HEAVY VEHICLES
Vehicles with twin axel or greater | Fatigue, motor vehcicle accident, unsecured load. | H22 | • Ensure that any items packed or loaded by Mirvac personnel are packed and secured safely. . | administration | • Do not direct or encourage the driver to work unsafely (e.g. speeding or driving while fatigued). | • Monitor vehcile and driver activity on site and adress any concerns immediately. Dock master available during Loading dock operation to monitor vehicle and staff activities | H14 | Asset Manager, Faciliaty Managent team, Service Providers | Heavy Vehicle National Law (HVNL) (See Relevant Jurisdiction - www.nhvr.gov.au) Heavy Vehicle (Fatigue Management) National Regulation Heavy Vehicle (Mass, Dimension and Loading) National Regulation Heavy Vehicle (Registration) National Regulation Heavy Vehicle (Vehicle Standards) National Regulation
HOT WORKS
Hot work (welding, burning or angle grinding) - | Fire Burns Property damage Environmental damage | H16 | • If possible, redesign the work methodology to a non-heat producing methodology; • Non-flammable screens to protect flammable substances from the work; • If welding/cutting, gas cylinders secured and have flashback arrestors fitted at torch and gas bottle on both hoses; • Hot Work Permit used and copy at location of work; • Trained and competent operator; • Fire equipment working properly and located within 2 metres of hot work; • Spotter in place with firefighting equipment; • Fire Equipment Register and maintenance program | Engineering | • A competent and experienced person has conducted a Risk Assessment of the proposed work and inspected the workplace. • Hot Work Permit issued in accordance with the Hot Work Procedure and discussed with the person undertaking the hot work. • Include potential of falling objects and hot material from overhead Hot Works in JSEA • Review of Hot Work Permit if work conditions or location changes. • Inspection during hot work task. • Permit closed out at conclusion of hot work • 12 monthly testing/ replacement of flashback arrestors Flashback arrestors fitted by competent person (e.g. plumber, welder) • Inspection of fire equipment carried out within last 6 months • Personnel trained in use of fire extinguishers | • On-site observation • Hot Work Permit at work location, all conditions comply H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\HSE\4.0 Implementation\4.6 Hazard notification reports\4.6.2 Permits to work\All Permits • Maintenance records | M10 | Asset Manager, Facility Managent team, Service Providers | WHS Regs 2011 section 56 - 59, Noise Safe Work Australia – Managing Noise and Preventing Hearing Loss at Work: Code of Practice AS 2436:2010 – Guide to Noise and Vibration Control on Construction, Demolition and Maintenance Sites; AS 1269:2005 Occupational noise management; AS 1270:2002 Acoustics-Hearing Protectors; Occupational Exposures MMR
LIGHTING
Lighting | Inadequate lighting causing Injuries to people, damage to property | M11 | • All designs to comply with Australian Standard Building Fit Out specifications. • Compliance with the relevant Australian Standard for LUX Levels • Task specific lighting in place as per SWMS / JSEA. | Engineering | • DOOR 4 inspection to verify sufficient lighting • Regular inspection of workplace. | • Regular lighting inspections undertaken with defects identified and reported. • Night audits completed (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Daily Site & Fire Stairs inspection\2020) + Monthly FCR36 | L2 | Asset Manager, Facility Managent team, Service Providers | NSW: Work Health and Safety Act 2011 (NSW) Work Health and Safety Regulation 2017 (NSW) Qld: Work Health and Safety Act 2011 (Qld) Work Health and Safety Regulation 2011 (Qld) ACT: Work Health and Safety Act 2011 (ACT) Work Health and Safety Regulation 2011 (ACT) AS 1680.1 Interior & Workplace Lighting AS 2293.1-2005 Emergency escape lighting and exit signs for buildings - System design, installation and operation
MANUAL HANDLING
Activities that may include lifting, lowering, pushing, pulling | Sprains, strains and damage to joints ligaments and muscles | H16 | • Consider safe access and use in the design phase (DOOR). • Assess the risk prior to any manual handling task. Plan the task and ensure pathways are clear. Use mechanical aid or trolley where possible. • Bulk loads must be secured on trolleys to prevent toppling. • Follow SWMS / JSEA for all hazardous manual tasks. | Elimination | • Training in correct manual handling techniques (incl. on-going toolbox talks, coaching) • Maintain mechanical aids. • Monitor hazardous manual tasks to enure compliance. | • Records of training H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\HSE\1.0 General\Toolbox Talks • On-site observation • Maintenance records | M10 | Asset Manager, Facility Managent team, Service Providers | Safe Work Australia: Hazardous Manual Tasks Safe Work Australia: Guide to managing risks of exposure to whole body vibration in workplaces Safe Work Australia: Guide to managing risks of exposure to hand-arm vibration in workplaces National Standard for Manual Handling [NOHSC:1001(1990)] National Code of Practice National Standard [NOHSC:2005(1990)] Work Safe ACT - Code of Practice - Work Health and Safety (Hazardous Manual Tasks) Work Safe NSW - Hazardous manual tasks - Code of Practice Work Safe Vic - Compliance code - Hazardous manual handling Work Safe QLD - Hazardous manual tasks - Code of Practice Work Safe WA - Manual tasks - Code of Practice
OCCUPATIONAL EXPOSURES
Heavy Metals/ Weld Fume | Illness to workers from long terms exposure | H16 | • Forced ventilation • Substitute welding with lower risk work practices • Respiratory protection • Hot works permit • Project personnel alerted to substances and risk of exposure; • HSE Manager trained in Mirvac Occupational Exposures Training • Occupational Exposures covered in Induction Training for all workers | Engineering | • JSEA/SWMS approval process considers required controls; • Required training occurs; | • Site Inspections and Audits; (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Daily Site & Fire Stairs inspection\2020) + Monthly FCR36 • Induction Records | M10 | Asset Manager, Facility Managent team, Service Providers | WorkSafe ACT - Work Health and Safety (Managing risks of hazardous chemicals in the workplace): Code of Practice Approval; Work Cover NSW - Spray painting and powder coating: Code of Practice Occupational Exposures MMR
OCCUPATIONAL NOISE
Noise | Hearing loss or damage. Discomfort to the community | M11 | • Noisy activities isolated from general work areas by noise barriers wherever possible • Personal hearing protection must be work as required in the SWMS / JSEA's • Use of noise minimising tools / equipment where possible. • Appropiate respite periods to be incorporated into the job schedule. | Engineering | • Audiometric testing for at risk employees if required to wear hearing protection on a frequent basis. • Noise monitor to be calibrated according to manufacturer’s instructions, and Occupational Noise MMR. • Inspection of isolation barriers • Noise monitoring included as part of inspection schedule. | • Records of Noise Monitoring; • Records of Calibration; • Records of hearing test programs • On-site observations (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Daily Site & Fire Stairs inspection\2020) + Monthly FCR36 | L2 | Asset Manager, Facility Managent team, Service Providers | WHS Regs 2011 section 56 - 59, Noise Safe Work Australia – Managing Noise and Preventing Hearing Loss at Work: Code of Practice AS 2436:2010 – Guide to Noise and Vibration Control on Construction, Demolition and Maintenance Sites; AS 1269:2005 Occupational noise management; AS 1270:2002 Acoustics-Hearing Protectors; Occupational Exposures MMR
SECURITY
Security Operations | Armed Hold up Injuries to people, damage to property | H20 | • Faclity type / tenant profile to be assessed for heightened threats. Additional controls to be included here as required. | Administration | • Discussions with Security contractor for appropriate controls as per level of threat. • Security Operations: Site Specific security procedures for various activities to be in place e.g. patrols, after hours procedure, JSEA for common activities- golf carts. | • Maintaining security procedures and business continuity plans. H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Contracts & Services\Security\Reports & Minutes\Monthly Service Provider Meeting Minutes • Security Operations: Completion of FCR37 at regular intervals. | M9 | Asset Manager, Facility Managent team, Service Providers | WHS ACT 2011 (s)20 Duties of PCBUs WHS Regulations 2011 Chapter 3 – General Risks & Workplace Management
STORM WATER DISCHARGE
Storm Water Discharge | Enviromental Damage | H15 | • Ensure that areas draining to the stormwater system are maintained and free from litter and debris. • Ensure that waste containers are provided in appropriate areas to prevent litter entering the stormwater system (for example ash trays and litter bins). • Ensure that all chemicals stored near stormwater drains are bunded to prevent leaks and spills from entering the stormwater system. | Engineering | • Provide a spill kit where appropriate, for example in car park, to ensure that oils, fuels and chemicals do not enter the stormwater system. • If appropriate, install trash racks, drain screens or separators to prevent stormwater becoming contaminated. | • FCR01 • FCR036 • Daily Operational Inspection (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Daily Site & Fire Stairs inspection\2020) | M9 | Asset Manager, Facility Managent team, Service Providers | NSW: Work Health and Safety Act 2011 (NSW) Work Health and Safety Regulation 2017 (NSW) Qld: Work Health and Safety Act 2011 (Qld) Work Health and Safety Regulation 2011 (Qld) ACT: Work Health and Safety Act 2011 (ACT) NSW Protection of the Environment Operation Act and Regulation Occupational Exposures MMR Environment MMR
TRAFFIC MANAGEMENT
Car park N/A Loading dock (B6) Pedestrian Management (limited pedestrian/vehicle separation marking on loading dock entry shutter) | Vehicular collision, people struck by moving objects, crush injuries and damage to property | H17 | • Implment Traffic Management Plan (TMP). • Pedestrians separated from moving plant/vehicles. • Loading Docks to be designed and operated to effectively separate pedestrian and vehicles. • Rules of operation established (e.g. speed limits, looking in direction of traffic, stopping at blind corners). | Isolation | • Where pedestrians and plant/vehicle can be separated- On-site observation/ Record of TMP and certificate of competency. • Where pedestrians and plant/vehicle cannot be separated - On-site observation/ Record of competency. • Issues and safety concerns to be raised and discussed at the tenant / retailer meetings | • Regular inspections undertaken using the MEX system of reporting and defect identification. (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Daily Site & Fire Stairs inspection\2020) • Appropriate signage / line marking/ barricades to be in place. | L5 | Asset Manager, Facility Managent team, Service Providers | WHS Regs 2017 section 291 (n) & (o) WHS Regs 2017 Part 4.5, section 81 - 112, High Risk Work AS/NZS 4602.1: High visibility safety garments - Garments for high risk applications AS/NZS 2890.1: Parking facilities Off-street car parking AS 1742.3: Manual of uniform traffic control devices Traffic control for works on roads AS 2578: Traffic signal controllers AS 1742.10: Manual of uniform traffic control devices Pedestrian control and protection Safe Work Australia – Workplace traffic management: Guidance Material (Series) Work Cover NSW – Moving plant on construction sites: Code of Practice Work Cover NSW – Safety in the road freight transport industry: Code of Practice Work Safe QLD - Traffic management for construction or maintenance work: Code of Practice Work Safe Vic - A Guidebook of Industrial Traffic Management & Forklift Safety Work Safe WA - Safe movement of vehicles at workplaces RMS (NSW) Traffic Control at Worksites Vic Roads Guidelines for Traffic Controllers Traffic Management MMR Plant Equipment & Tools MMR
WORK AT HEIGHT traffice Management MMR
Mobile scaffolds | Falls from a height | H20 | • Mobile scaffold installed as required including sturdy structure, fully planked, internal access with trapdoor, handrail min 900 mm, mid-rail and toe boards. • Mobile scaffolds are away from edges and penetrations • Personnel removed, tools and equipment secured prior to moving • Brakes/castor wheel locks applied whilst scaffold is in use | Engineering | • If over 4 metres, erected by licenced person • Handover certificate provided (for scaffolds over 4 metres) • Inspection of scaffold every 30 days by licenced (if > 4 m) or competent person or after adverse weather conditions • Minimum 1 metre back for every 1 metre in height of the scaffold platform | • Records of Licence (if over 4 metres) • Records of certificates • On-site observation | H15 | Asset Manager, Facility Managent team, Service Providers | AS/NZS 1891.4:2009 Industrial Fall Arrest Systems & Devices WHS Regs 2011 section 291 (a) WHS Regs 2011 Part 4.5, section 81 - 112, High Risk Work WHS Regs 2011 section 225 - Scaffolds WHS Regs 2011 Part 4.4, sections 78 - 80 AS/NZS 4576:1995 - Guidelines for Scaffolding; AS 1577:1993 - Scaffold Planks AS/NZS 1576.1:2010 Scaffolding - General Requirements Work at Height MMR Work at Height MMR Reference Document
Other Fall Prevention Strategies | Falls from a height | H16 | • For all tasks 2.0 metres and over, identified as having potential for persons to fall. • Risk Assessment to identify the most appropriate fall prevention method for the location specific task, including 'fall restraint' & 'travel restraint' utilising the Hierarchy of Control. • Emergency Rescue Plan (ERP) incorporating a Retrieval Plan developed | Administration | • Task personnel are involved and trained in the location/task specific JSEA (or equivalent) & ERP; • Task personnel have attended recognised Fall Equipment training to "Work Safely at Height" • Include potential of falling objects and hot material from overhead Hot Works in JSEA • Correct installation & use of appropriate fall arrest equipment identified above | • JSEA (or equivalent) & ERP with Retrieval Plan for specific task/location • Statement of Attainment - Work Safely at Height • Task personnel have Statement of Attainment - Work Safely at Height Licence for record saved to Service provider staff files | M9 | Asset Manager, Facility Managent team, Service Providers | Refer Legislation, Standards and Codes in I 121 WHS Regs 2011 section 291 (a) WHS Regs 2011 Part 4.5, section 81 - 112, High Risk Work WHS Regs 2011 section 54 - 55, Falling Objects WHS Code of Practice - Managing the Risk of Falls at Workplaces; Model Code of Practice Construction Work, Safe Work Australia; The National Code of Practice for the Construction Industry, Asutralian Building and Construction Commission; NSW: Work Health and Safety Act 2011 (NSW) Work Health and Safety Regulation 2017 (NSW) Vic: Occupational Health and Safety Act 2004 (Vic) Occupational Health and Safety Regulations 2017 (Vic) Qld: Work Health and Safety Act 2011 (Qld) Work Health and Safety Regulation 2011 (Qld) ACT: Work Health and Safety Act 2011 (ACT) Work Health and Safety Regulation 2011 (ACT) Scaffolding and Lifts Act 1912 (ACT) Scaffolding and Lifts Regulation 1950 (ACT) WA: Occupational Safety and Health Act 1984 (WA) Occupational Safety and Health Regulations 1996 (WA) SafeWork Australia – Model Code of Practice: Managing the risk of falls at workplaces 20-15 SafeWork Australia - Guide to formwork SafeWork Australia - Model Code of Practice: Preventing falls in housing construction SafeWork Australia - Model Code of Practice: Safe design of structures SafeWork Australia - National Standard for construction work SafeWork NSW - Managing the Risk of Falls at Workplaces SafeWork NSW – Preventing falls in housing construction code of practice Workplace Health & Safety QLD - Managing the risk of falls at workplaces Workplace Health & Safety QLD – Formwork Code of Practice | Workplace Health & Safety QLD – Scaffolding Code of Practice SafeWork SA - Managing the Risk of falls at workplaces code of practice Fact Sheet ; WorkSafe VIC - Prevention of Falls in General Construction WorkSafe VIC – Guidance Note: Prevention of Falls – Ladders WorkSafe VIC - Outdoor advertising material safe installation and removal WorkSafe WA - Prevention of Falls at Workplaces AS/NZS 4994.1Temporary edge protection - Part 1: General requirements AS/NZS 4994.2 Temporary edge protection - Part 2: Roof edge protection - Installation and dismantling AS/NZS 4994.3 Temporary edge protection - Part 3: Installation an dismantling for edges other than roof edges AS/NZS 4994.4 Temporary edge protection - Part 4: Temporary edge protection – Perimeter protection screens AS/NZS 1576.1Scaffolding general requirements AS/NZS 1576.2 Scaffolding Couplers and Accessories AS 1576.3 Scaffolding Prefabricated and tube-and-coupler scaffolding AS 1576.4 Scaffolding Suspended scaffolding AS/NZS 1891.4 Industrial fall arrest systems and devices AS/NZS 4389 Safety mesh AS/NZS 4576 Guidelines for scaffolding AS 3610 Formwork for concrete AS 1319 Safety Signs for the Occupational Environment AS 2550.10 Cranes, hoists and winches – Safe use Mobile elevating work platforms AS 2550.1 Cranes, hoists and winches – Safe use General requirements AS 2550.19 Cranes, hoists and winches – Safe use Telescopic handlers AS 1418.1 Cranes, hoists and winches General requirements AS 1418.10 Cranes, hoists and winches: mobile elevating work platforms AS 1418.17 Cranes (including hoists and winches) Design & construction of workboxes AS1657 Fixed platforms, walkways, stairways and ladders – Design, construction and installation AS/NZS 4488.1 (R2017) Industrial rope access systems Selection, use and maintenance AS/NZS 4488.1 (R2017) Industrial rope access systems Specifications
Ladders No Ladders kept on site | Falls from height/ falling objects | H16 | • Platform ladders to be used. If platofrm ladder cannot be used a risk assessment is to be completed. • All ladders to have an annual inspection and have a Mirvac compliance sticker • Restricted use of ladders, especially near open penetrations, edges, stairs or balconies • No climbing above 3rd highest rung, use 3 points of contact and chest to remain within stiles of ladder | Engineering | • Visual inspection of ladders • Ladder rated for industrial use (120 kg max), minimum 1.2 metres and in good condition. • Where repeated access to heights of 2 metres or more is required, an elevated work platform, (e.g. mobile scaffold or other) is used instead of a ladder, or handrail erected where ladder near an edge | • "Inspection before each use" included as Control Measure in JSEA for task • Included in Induction topics • On-site observation | M10 | Asset Manager, Facility Managent team, Service Providers | AS/NZS 1892.1:1996 – Portable ladders Part 1: Metal; AS 1892.2:1992 – Portable ladders Part 2: Timber; AS/NZS 1892.3:1996 – Portable ladders Part 3: Reinforced plastic; AS/NZS 1892.5:2000 – Portable ladders Part 5: Selection, safe use and care. Work at Height MMR Work at Height MMR Reference Document
VISITORS
Visitors | Injuries to visitors | H20 | • ALL visitors to be escorted while on the premises. • Relevant safety concerns and issues to be advised to visitors by escorting agent. NB: Visitors who frequent (more than once) site must be inducted. | Engineering | • All visitors to sign in and out when entering and exiting the premises. | • FM and HSE to regularly review CMS for compliance. | M6 | Asset Manager, Facility Managent team, Service Providers | WHS Act 2011 (s)20 Further Duties of PCBUs WHS Regulations 2011 Chapter 3- General Risk & Workplace management Office & Industrial Service Provider Management Procedure
ENVIRONMENTAL ASPECTS
AIR QUALITY
Indoor and outdoor air quality (annual air quality testing conducted by IMC) | Adverse reactions by tenant, public and employees to chemicals, particles and/or substances in the air | H16 | • Minimise dust released by disturbance of soil and/or gaseous emissions from operation of plant and equipment or vehicles. • Provide clean, healthy, fresh air to facility at all times. • Ensure adequate ventilation. • Ensure recommended chemicals and treatments are used in the correct quantities at all times. | Engineering | • Testing for bacteria, CO’s, temp and humidity on an annual basis in accordance with relevant AS. Reports reviewed for any out of parameters levels which require corrective action and the records to be kept on file. • Service provider engaged to carry out testing must provide written report which FM is to review for out of parameter levels, addressing corrective action where required. • Manufacturers recommendations for safe use of products - Safety Data Sheets (SDS) and equipment to be adhered to for processes within buildings that may affect air quality i.e. dry cleaning, generators etc. • Plant inspected on arrival to site. • Daily pre-start completed. • Inspection and maintenance as per manufacturer's requirements. • Minimise stockpile heights. • Stabilise long term stockpiles e.g. grass/ hyrdomulch | • FM to ensure annual testing of IAQ, or at more frequent intervals if deemed necessary. (H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\HSE\5.0 Measurement and Evaluation\Indoor Air Quality Reports) • Monthly testing of water system quality. H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Cooling Towers\Test Results • Water treatment service Provider to be regularly monitored to ensure the Cooling Tower Manual compliance is maintained and completed as required. H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Cooling Towers\Test Results\2020\Water Treatment Test • On-site observation • Maintenance records available | M10 | Asset Manager, Facility Managent team, Service Providers | Safe Work Australia – National Code of Practice for the Safe Use of Synthetic Mineral Fibres NOHSC:2006(1990)] Refer cell I 261 for environmental - related Legislation, Standards, Codes Plant Equipment & Tools MMR; Occupational Exposures MMR;
RESOURCE MANAGEMENT
Potable Water | Depletion of non-renewable resources | M11 | • Identify opportunities to reduce potable water consumption in facilities where Mirvac Facility Management have operational control. • Deliver on the Mirvac 'This Changes Everything' strategy to implement a 5% reduction in potable water intensity by FY23. | Administration | • Monitor and report on building potable water consumption. • Perform annual NABERS Water ratings to benchmark performance. • Investigate new water efficiency technologies. | • Monitor building daily usage profiles generated from smart meter data. • Perform a comparison review of monthly water consumption generated from smart meter data. • Review historical quarterly water consumption data from invoices and meter data. • Review and analyse annual NGERS data. H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Utilities\Consumption Records | L3 | Asset Manager, Facility Managent team, Service Providers | Environmental Management MMR
Energy | Depletion of non-renewable resources Emissions of Greenhouse Gases | M11 | • Identify opportunities to reduce energy consumption and Greenhouse emissions in facilities where Mirvac Facility Management have operational control. • Deliver on the Mirvac 'This Changes Everything' strategy to implement a 5% reduction in carbon intensity by FY21. | Administration | • Monitor and report on building energy consumption and Greenhouse emissions • Perform annual NABERS Energy ratings to benchmark performance. • Investigate new energy and carbon efficiency technologies. | • Monitor building daily usage profiles generated from smart meter data. • Perform a comparison review of monthly water consumption generated from smart meter data. • Review historical quarterly water consumption data from invoices and meter data. • Review and analyse annual NGERS data. H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\Utilities\Consumption Records | L3 | Asset Manager, Facility Managent team, Service Providers | Environmental Management MMR
SPILLS OR DISCHARGE CAUSING CONTAMINATION
Storage and Handling of Hazardous Substances and/or Dangerous Goods | Spills or discharge causing contamination Injury/Illness of Member of Public, Contractor or Worker | H17 | • Substances/goods stored in accordance with Safety Data Sheet (SDS)/(MSDS) • Storage area bunded and away from drainage inlets or other sensitive areas. • Substances/goods stored and handled in accordance with SDS (MSDS). • Appropriate PPE made available. • Users trained in correct use of substance. | Engineering | • Signage and emergency response equipment available relevant to the class of substance/good stored. • Nominated personnel trained in spill response. • Bunding designed to meet required 110% of largest individual container. • No fuel storage within 50 metres of a water body. • Spill Kit available. • Minor quantities only stored which do not require licencing. • Pressurised gas cylinders/bottles secured from toppling and stored in ventilated area with restricted access. | • Spill Kit stocked H:\Investments\Assets\Office & Industrial\NSW\Properties\101 Miller Street-Tower\Operations - New\HSE\1.0 General\First aid & Spill Kit List • Records of spill response training available • On-site observation • Drainage outlet to bunding locked | M10 | Asset Manager, Facility Managent team, Service Providers | WHS Regs 2011 AS 1940:2004 Storage and Handling of Flammable and Combustible Liquids AS 4452:1997 Storage and Handling of Toxic Substances Safe Work Australia - NOHSC: Approved Criteria for Classifying Hazardous Substances - [NOHSC:1008] Safe Work Australia - NOHSC: National Code of Practice for the Labelling of Workplace Substances - [NOHSC: 2012]. Safe Work Australia - National Standard - Storage and Handling of Workplace Dangerous Goods - [NOHSC: 1015] Safe Work Australia - Guidance Note - Placarding Stores for Dangerous Goods & Specified Hazardous Substances - [NOSHC:3009] Safe Work Australia - National Model Regulation for the Control of Workplace Hazardous Substances - [NOHSC:1005] Safe Work Australia - National Code of Practice for the Control of Workplace Hazardous Substances - [NOHSC:2007] WorkSafe ACT - Work Health and Safety (Labelling of Workplace Hazardous Chemicals: Code of Practice) Approval Occupational Exposures MMR
WASTE
Recycles • general and prescribed waste (solid & liquid) Recycling - 2019 @ 79% | Non-compliance and breaches of EPA regulations | H16 | • Waste is minimised & stored securely • Waste generated is collected and recycled in accordance to the Waste Management Hierarchy. • Waste is managed and stored securely. Waste material is disposed of by reputable contractors in accordance with legislative requirements. • Deliver on the Mirvac 'This Changes Everything' strategy to implement a 85% recycling rate across the Investment portfolio by FY23. | Engineering | • Waste storage facilities established according to estimated volume including paint tanks and recycling bins/skips for all streams. • Waste sorted on site or at the waste depot. • Transporter and receiver of waste are EPA Licensed. • Waste transport certificate is obtained (this verifies waste was disposed of in the correct facility) e.g., Adhesives (excluding solid inert polymeric materials), Lime sludges or slurries, Paint sludges and residues, Pesticides (including herbicides & fungicides), Timber preservative residues. • Mirvac require waste contractors to only utilise appropriately licenced facilities and to declare these facilities to Mirvac with the licencing details. • Mirvac investigate and implement applicable waste management and recycling technologies. • Waste Management Plans for each asset where Mirvac Retail manage waste services. • Perform waste audits to identify waste minimisation and recycling opportunities. | • Monthly waste records including quantities diverted from landfill to recycling • Records of licences. • Review of service provider JSEA for works which constitute a “material risk to environment/ generate significant wastes streams” prior to commencement of work. • Records of certificates of disposal from waste removal contractor which are forwarded to the Sustainability data collection point. • Hold regular meetings with waste contractors. • Review historical quarterly water consumption data from invoices and meter data. • Review and analyse annual NGERS data. | L5 | Asset Manager, Facility Managent team, Service Providers | Plant Equipment & Tools MMR; Occupational Exposures MMR; Safe Work Australia – National Code of Practice for the Safe Use of Synthetic Mineral Fibres NOHSC:2006(1990)]; Safe Work Australia - National Standard - Storage and Handling of Workplace Dangerous Goods - [NOHSC: 1015] Safe Work Australia - Guidance Note - Placarding Stores for Dangerous Goods & Specified Hazardous Substances - [NOSHC:3009] Safe Work Australia - National Model Regulation for the Control of Workplace Hazardous Substances - [NOHSC:1005] Safe Work Australia - National Code of Practice for the Control of Workplace Hazardous Substances - [NOHSC:2007] Safe Work Australia – National Code of Practice for the Control of Scheduled Carcinogenic Substances - [NOHSC:2014] Refer cell I 210 - 212 for environmental - related Legislation, Standards, Codes
Note on A4: Amanda Reid: (Potential cause of injury/illness or cause of damage to the environment – as identified on Hazard/Aspect Worksheet)
Note on B4: Amanda Reid: (What could happen)
Note on D4: Amanda Reid: (According to Hierarchy of Controls, Elimination of the hazard/aspect is our primary objective)
Note on F4: Amanda Reid: (What we need to do to ensure the Controls are implemented, effective & operational)
Note on G4: Amanda Reid: (What tools are used to monitor the critical controls and critical activities for effectiveness)
Note on J4: Amanda Reid: (Statutory requirements from Commonwealth or State Government, Council Ordinances, Regulations, By-laws, EPA, Australian Standards and Codes of Practice, relevant to each Critical Control)
Note on D55: Amanda Reid: What is the O&I version Melanie Jones: Confirmed with Al Lutzke no specific O&I document is in place, we would reference AS.
Note on J67: Amanda Reid: Check if referencing correct mmr

## Sheet1 (hidden)
L1
L2
L3
L4
L5
M6
M7
M8
M9
M10
M11
M12
M13
H14
H15
H16
H17
H18
H19
H20
H21
H22
E23
E24
E25

## MAJOR HSE RISKS
Asset Name: Hoist Tenancy
Date: 30/01/2020
Prepared By: Jake Field & Matt Wiley
Note: Insert the top 5 HSE risks for your Asset and or any unusual HSE risk
Risk Hierarchy: E = Extreme, H = High, M = Medium, L = Low
Description Provide a description of the identified task or operation | Upcoming, active or closed | Hazard/Risk | Untreated Risk | Risk Mitigation Strategy Provide a summary of the risk mitigation strategy action | Monitoring Activities Provide a summary of how the risk mitigation strategy action will be monitored | Residual Risk | Person / Team Member to Monitor | Changes/ Reviews | Comments Provide any other general comments as required
PLANT ROOMS • Main Plant Room (L19, 20, 30, 31, 32, 33[roof]) • Sprinkler Valve Room (B1) • Switch Rooms (all floors - main switch room B1) • Lift Motor Rooms (L20, 31, 33) • Fire Control Rooms (B1, mimic panel in BM office) |  | Injuries to people, damage to property |  | All plant and switch rooms are to be locked, secure with access keys to be restricted. Unauthorised access to be prevented. Plant rooms to be free from unnecessary items and must contain sufficient lighting and appropriate signage installed at entries | Regular security checks to be undertaken to ensure enclosures remain locked and secure. Security conduct patrols. Plant rooms have striker plates as fire stairs are external. Completion of FCR36 and appropriate tenant inspections where required |  | FM
WORKING AT HEIGHTS • Internal / external glass cleaning • Industrial rope access • Window Cleaning Profesionals conduct internanl and external clean via anchor points and ropes, testes and setified by NHSS |  | Falls from height/ falling objects |  | FM to engage appropriately qualified Industrial Rope Access (IRA) consultant to carry out cleaning & inspections of internal/external facades. Level 2 required for building All roof access to be controlled. Roof access permit. Conducted with FM on CMS avalible via rapid Works as per WCP SWMS 001 document avalible via rapid Certified anchor points. Annualy by NHSS | FM to routinely check roof access during property inspections. access is securied via Access pass through lift. GMK key through fire doors and padlock on external doors to roof area. On-site observation. Roof Access permit for roofs in excess of 2 storeys. Fall restraint equipment register. Record of inspection by a competent person at maximum 6 month intervals for safety harness and max 3 months for wire ropes or other fall arrest equipment. NHSS Anchor point(s) certified prior to use or at max. 12 month intervals. NHSS Training in the use of fall arrest equipment verified. licence inspected and quoted on permit. |  | FM
CONFINED SPACES • Grease traps (Located B2 Changroom) • Pits (10 x Lift Shafts) • Storage & Retention & Drainage Tanks (11 x tanks and pits) • Cooling towers (3 x CT Located Level 33 |  | Injury or Emergency when in a confined space |  | Confined spaces labelled and access restricted (e.g.. signage, barricade). Current Confined Space Permit issued and kept at location of confined space entry. Entry to Confined Space as per conditions on the permit (e.g., daily pre-start brief, gas testing, log for entry and exit, ventilation, temperature). Standby person at confined space entry point controls entry and exit. Personnel that enter confined space and standby person are confined space trained (by RTO with confined spaces in their scope). | Record of training. Record of Risk Assessment. On-site observation. Register of confined spaces. Register of persons entry/exit to space. Records of evacuations and training drills. |  | FM
ELECTRICAL WORKS • Electrical Installation (switch board) • Supply (transformer) • Installation of electrical equipment • Electrical Welding |  | Electrocution, burns, fire or damage to property due to faulty or poorly maintain equipment |  | All portable electrical equipment, which includes all equipment and appliances that are connected to the electricity supply [240 – 415v] by a flexible cord, including portable power supplies, extension cord sets and power boards, also fixed and portable Residual Current Devices (RCD) installed and used in accordance to AS/NZS 3760-2010 and AS/NZS 3012-2010. Annual RCD testing conducted September as per maintenance schedule results located on H-drive Mirvac Group Electrical Inspection & Testing Guidelines, MO&I Thermographics and Isolation procedures to be adhered to. Test and Tag conducted Annualy in August. Determine if any onsite transformers are owned by either the electrical authority or Mirvac. | FM to engage licensed electrical contractor to carry out Annual Thermography Scans and testing and tagging as required. FM to confirm isolation stickers are on all boards to remind workers of isolation procedure. Review operation manual provided by the supplier of the transformer to determine inspection and maintenance requirements to ensure safe ongoing operation and engage suitably qualified contractor to undertake the works. FM to under regular inspection of workplace as per FCR36. |  | FM
HAZARDOUS SUBSTANCES Flammable Goods - 11,000L Fuel tank located B2 Chemicals |  | Injuries or damage to property from Fire/Explosion |  | Mirvac Group guidelines to be implemented where a workplace stores or uses Dangerous Goods. Untrained people not to use or determine storage requirements for hazardous substances or dangerous goods. Products stored in approved cabinets or purpose built containment areas. Hazardous Substance Risk Assessment HSEF2.25 (HSRA) completed including research and purchase of less hazardous/ dangerous products. SDS to be obtained and are not over 5 years old Incompatible HS/DG are stored separately. Flammable goods to be stored in a flammable goods cabinet. Chemicals to be bunded to 110% of largest quantity. Spill Kit available. level 33 and 3 | Hazardous Materials Management Plan to be developed. Hazardous Materials - 5 yearly inspection of areas containing Asbestos by a competent person. A Register of all Hazardous Materials to be kept on site.
Major HSE Risks from the Risk Register

## Biological
BIOLOGICAL
Infection control | Exposure to blood borne infectious diseases | H16 | • Ensure blood/faeces are cleaned up immediately after reporting, ensuring cleaners adherence to their own company procedures. • Ensure hypodermic needles, syringes, condoms or other, are collected immediately after they are reported utilising the recommended containers and tools as per SWMS / JSEA. | Elimination | • Provide appropriate training, equipment and PPE for managing biological hazards. • Dispose of biological waste in accordance with SWMS / JSEA. | • Service Provider to be regularly monitored to ensure activities are completed as per the SLA. | L3 | Asset Manager, Facility Management team, Service Providers | WHS Regulation 2011 (s)42 First Aid AS4031 Non-reusable containers for the collection of sharp medical items used in health care areas. National Code of Practice: Control of Work Related Exposure to Hepatitis and HIV (blood-borne) Viruses [NOHSC: 2010 (2003)]
| Exposure to infectious viruses | H19 | • Ensure Government guidelines on physical distancing can be achieved in the workplace. • Ensure that appropriate signage is displayed advising of conditions of entry and physical distancing requirements within the asset. People who are unwell will not be permitted access. • Ensure all contractors confirm compliance with control measures prior to accessing the asset. • Ensure that all high touch points are disinfected on a regular basis each day in accordance with Department of Health cleaning standards. • Ensure adequate sanitary, cleaning and PPE supplies are available. • Ensure building occupants are aware that they must report a suspected or confirmed case to building management immediately. • Ensure social distancing is maintained at seating areas (apply signage to fixed furniture, remove furniture where appropriate). • Ensure sanitisation stations are available in each lobby / EOT. | Elimination | • Provide appropriate training, equipment, PPE and resources for managing infectious viruses. • Ensure that potentially contaminated areas are disinfected immediately following a report of a suspected or confirmed case. • Ensure contact tracing is undertaken and relevant parties notified as soon as practicable. • Ensure infected individuals isolate for 14 days and obtain medical clearance before returning to the workplace | • Service Provider to be regularly monitored to ensure activities are completed as per the SLA. • Monitor reports from tenants. | L3 | Asset Manager, Facility Management team, Service Providers | Safework Australia - COVID for workplaces Australian Government Department of Health World Health Organization website. NSW Health Victoria Health and Human Services QLD Health WA Department of Health