## Risk Ranking
LIKELIHOOD (L) |  |  | CONSEQUENCE (C) - IMPACT |  |  | RISK RANKING (R) | [5 empty] | Risk Ranking Summary
[7 empty] | 1 | 2 | 3 | 4 | 5 | EXTREME-These risks are Unacceptable. The work activity should be halted until Critical Controls are implemented which reduce the risk to no greater than High. If it is not possible to reduce the risk, the work should remain prohibited.
A | Almost Certain | Expected to be the outcome in most cases - 91 - 100% probable | 1 | Insignificant | First aid injury/s (FAI), minor environmental impact. Minor/ medium term social impacts on local population, or expected financial impact = < $10k. | A | M (8) | M (13) | H (18) | E (23) | E (25)
B | Likely | Will probably occur in most circumstances - 51 - 90% probable | 2 | Minor | Medical Treatment Injury (MTI), minor short term environmental impact. Attention from media & heightened concern by local community or expected financial impact = $10k - $100k. | B | M (7) | M (12) | H (17) | H (21) | E (24) | HIGH-These risks must be reduced where possible by implementing higher levels of Critical Control using the Hierarchy of Controls. Where the residual risk is not able to be reduced lower than High, a controlled work methodology must be in place and reviewed by the HSE Lead and Workplace Manager.
C | Possible | Might occur some time 31 - 50% probable | 3 | Moderate | Lost Time Injury (LTI). Serious irreversible injury/disease, serious medium term environmental harm. Adverse local media coverage, or expected financial impact = $100k - $1 mill. | C | L (4) | M (11) | H (16) | H (20) | H (22) | MEDIUM-Identified Critical Controls must be capable of reducing the risk by eliminating or minimising to an acceptable level. # Critical Activities & Monitoring are to be identified and implemented by Supervisory staff.
D | Unlikely | Could occur, but would not be expected - 10 - 30% probable | 4 | Major | Single fatality, permanent localised environmental harm. Substantial risk to corporate reputation, sustained adverse local media coverage, major repairs or project outcomes affected, or expected financial impact = $1 - 10 mill. | D | L (3) | M (6) | M (10) | H (15) | H (19) | LOW-The work is relatively safe and can be managed by following routine MMRs, procedures, guidelines & JSEA/SWMS. No further action is required, unless additional hazards arise during the work.
E | Rare | Rare that this would occur - no previous occurrence in similar circumstances - < 10% probable | 5 | Catastrophic | Multiple fatalities, permanent long term and extensive environmental harm. Extreme risk to corporate reputation, public outrage & national media coverage, high profile litigation, class action, threat to business division viability or expected financial outcome = $10 - $100 mill. | E | L (1) | L (2) | L (5) | M (9) | H (14) | HIERARCHY OF CONTROLS Eliminate - remove hazard completely; Substitute - replace with less hazardous; Isolate - separate the worker from the hazard Engineer - guarding, mechanical aids, ventilation; Administrate - reduce exposure, procedures, consultation; PPE - to be used in addition to above.
Mirvac HSE
Element 3 - Risk Management
Risk & Assessment Register
Mirvac HSE
Element 3 - Risk Management
Risk & Assesment Register

## EV Charger Equipment Assessment
No | EV CHARGER EQUIPMENT ASSESSMENT GUIDE (Review your EV Charger equipment against the below - if you you answer "NO" to any questions 1-4, please reach out to your SFM or Divisional Manager to review the current EV equipment, your equipmnt may need to be upgraded) | YES | NO
1 | Ensure EV Charge is fitted with constant communications to control charging which is an ISO standard and means it is not possible for a charger to provide too much power to a vehicle, nor it is possible to “overcharge” the battery as the vehicle will shut off the power once it has reached >99% state of charge. If a vehicle does not operate in line with the ISO standard the charger can and will also prevent any power delivery. | YES | Not optional - this is a must have
2 | Ensure system is installed under Australian Standards, which will ensure if a fault is detected in the system the upstream RCD and circuit breaker will cut power between the charging infrastructure and upstream power supply at the switchboard. | YES | Not optional - this is a must have
3 | Review system for an inbuilt monitoring system that can detect earth leakage, overcurrent and short circuits. Should there be a traction fire battery fire this will trigger the short circuit and/or the overcurrent protection and isolate power at the charger | YES | Not optional - this is a must have
4 | Ensure as per Australian Standards a accessible Emergency Stop button and isolator switches are installed in case there is need for intervention | YES | Not optional - this is a must have
5 | Where possible look to ensure either a cloud based approach to technology and charger operations, a charger would have a CAN bus communication network that takes in data from numerous sensors in all key components. This data is then fed back to a management system so that technicians can remotely investigate and resolve many issues as way as automatically triggering repairs and preventitive maintenance requirements. | YES

## EV Risk & Assessemnt Register
Team members: (Initial team, then members in each revision team) | Date created for this workplace: |  | Date of This Revision: |  | Workplace: |  |  | Division: Retail
Current Revision:(A, B,……)
Identified Hazards and Aspects (Potential cause of injury/illness or cause of damage to the environment – as identified on Hazard/Aspect Worksheet) | Risk (What could happen) | Untreated Risk | Critical Controls (According to Hierarchy of Controls, Elimination of the hazard/aspect is our primary objective) | What is the highest level of Hierarchy of Controls? | Critical Activities (What we need to do to ensure the Controls are implemented, effective & operational) | Monitoring Activities (What tools are used to monitor the critical controls and critical activities for effectiveness) | Treated Risk | Designated Person for treating and managing risk (position) | New South Wales, Queensland & ACT Legal and Other Requirements (Statutory requirements from Commonwealth or State Government, Council Ordinances, Regulations, By-laws, EPA, Australian Standards and Codes of Practice, relevant to each Critical Control) | Victoria Legal and Other Requirements (Statutory requirements from Commonwealth or State Government, Council Ordinances, Regulations, By-laws, EPA, Australian Standards and Codes of Practice, relevant to each Critical Control)
EV - LiB thermal Runaway Hazards | Access for the Fire Brigade to location of EV Chargers & Awarness Lack of Ventilation & Emergency Egress Proximity to essential services & flammable or explosive items Fire suppression systems EV Charger equipment maintenance, commissioning and system safety capabilities | H (18) | Ensuring there is a clear pathway to treat vehicle in the event of incident All Emergency access & egress points must be clear of obstructions at all times. Adequate ventilation mechanical and/or natural is in place At the time of design and construction the property complied with relevant AS, BCA or construction guidance - (Ordinance 70 if prior to AS). Identify the location of any essential services, gas lines, MSR’s, FCR’s, fuel storage, flammable materials & chemical storage prior to installation. No essential services to be within 15m of the closest EV car charging bay Adequate water supply availability Fire Sprinkler system in place / Fire Hydrant system in place / Fire Hose Reels in place / Fire Extinguishers in place Ensure high quality equipment is installed and that it has highest level of safety built in to the system (see additional tab - EV Charger Equipment Assessment) EV charger system reporting, analysis and alarming system capability Installation and commissioning certification obtained prior to energisation Bollards and wheel stops in front of charging equipment | Administration | Ensure location is risk reviewed prior to approval Ensure EV Charger locations are displayed within the Fire Control Room Ensure mechanical ventilation is in place and maintained Workplace Inspections undertaken according to Mirvac schedules. No essential services to be within 15m of the closest EV car charging bay, ensure future works consider EV Chargers Ensure fire systems are in place and maintained Ensure equipment is risk reviewed prior to approval of installation to confirm quality of the equipment and that the safety within the system is of premium quality Confirmation of reporting and alarming is enabled Ongoing maintenance requirements for EV equipment (minimum annual maintenance scheduled) | Include EV inspection regime for security & onsite operations teams FCR36 - Inspection of EV chargers Quarterly contractor engagement confirming maintenance task have been completed Records of maintenance and Essential Services certification Records of Workplace inspections. | L (4) | Mirvac Workplace Managers, Service Providers | Refer to standards & requirements within current Risk & opportunity Register for: - Fire and Emergency Egress - Electrical Installation - Fire - Air Quality | Refer to standards & requirements within current Risk & opportunity Register for: - Fire and Emergency Egress - Electrical Installation - Fire - Air Quality
Mirvac HSE
Element 3 - Risk Management
LiB Risk Assessment Register

## Risk & Opportunity Register
RISK & OPPORTUNITY REGISTER
Risk Ranking - Insert the "Untreated Risk" from the "Hazard / Aspect Worksheet" and then, according to the "Critical Controls" listed, and using the Risk Ranking matrix (Section 1) assess the "Treated Risk Ranking" appropriate to each row.
Appropriate R & O Register Hazards/Aspects and Critical Controls to be included in all workplace activity JSEAs (or equivalent)
Identified Hazards and Aspects (Potential cause of injury/illness or cause of damage to the environment – as identified on Hazard/Aspect Worksheet) | Risk (What could happen) | Untreated Risk | Critical Controls (According to Hierarchy of Controls, Elimination of the hazard/aspect is our primary objective) | What is the highest level of Hierarchy of Controls? | Critical Activities (What we need to do to ensure the Controls are implemented, effective & operational) | Monitoring Activities (What tools are used to monitor the critical controls and critical activities for effectiveness) | Treated Risk | Designated Person for treating and managing risk (position) | Legal and Other Requirements (Statutory requirements from Commonwealth or State Government, Council Ordinances, Regulations, By-laws, EPA, Australian Standards and Codes of Practice, relevant to each Critical Control)
ACCESS & EGRESS
Fire & Emergency egress | Confusion Lack of control Trips and Falls Fatalities | H17 | At the time of design and construction the property complied with relevant AS, BCA, NCC or construction guidance - (Ordinance 70 if prior to AS). All Emergency access & egress points must be clear of obstructions at all times. All emergency and exit lighting is operational. Regular Tests and Evacuation drills are conducted. A current Emergency Response Plan is in place and understood Resident handbook includes exits and emergency exits and assembly points Map of exits and assembly points accessible in the LIV App | Engineering | Fire audit to confirm compliance. Workplace Inspections undertaken according to Mirvac schedules. Emergency lighting maintenance undertaken. Contracts established to undertake fire drills and inspections to meet regulations. Annual review of Emergency Response Plan | Records of Fire audits and Compliance certificates. Records of Workplace inspections. Records of evacuation drills, current evacuation diagrams and signage. Evaluation of evacuation to be conducted after every evacuation exercise. | M6 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers | Mirvac Legal Register
Public access around hazardous activities | Cleaner, Service providers, Residents, General Public & Workers activities creating hazards | M12 | Exit signage Regular rotations of the area from Security, Building Management and Cleaners to ensure area is safe. Resident handbook includes exits and emergency exits and assembly points Map of exits and assembly points accessible in the LIV App Inductions to cover Mirvac's requirements. Where required SP & maintenance to erect adequate barricades/ hoardings/ signage in accordance with agreed JSEA/SWMS. | Isolation | Mirvac staff aware of all activities in public areas, JSEA/SWMS checked suitable for designated area. Mirvac inspection of compliance undertaken during set up. | Evidence of JSEA/ SWMS review for task/ location suitability. Records of Workplace inspections. | M6 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Safe access though public areas/common areas | Slips, trips & falls | H16 | Floors to be designed to have compliant slip resistanmce Cleaning regime to adapt quickly to weather or spills and undertake contracted routine cleaning. Slippery surfaces to be identified and managed. Cleaners, Building Management and Security to be given instruction on what to do if they see a spill or hazard. | Administration | Annual slip testing to take place Workplace Inspections undertaken according to Mirvac schedules and service provider cleaning agreement. | Building staff/ Security & Cleaners to undertake inspections at various times throughout the day and report any issues to cleaners. STF incidnts reporetd in Incident managgement system along with relevant correctoive actions Cleaning rotation inspections as per SLA. Signage as required from JSEA. Records of Workplace inspections. Current cleaning contracts regularly checked for suitability and kept on file. | M6 | Workplace Manager, Facility Manager, Building Management Staff, Service Providers
AIR QUALITY
Indoor and outdoor air quality (Amentlty Floors,Wellness areas, Mirvac offices) | Adverse reactions by residents, visitors, public or employees to chemicals, particles and/or substances in the air | H16 | Provide clean, healthy, fresh air to facility at all times. Ensure adequate ventilation. Ensure recommended chemicals and treatments are used in the correct quantities at all times. Filters are cleaned on a regular basis | Engineering | Testing for bacteria, CO’s, temp and humidity on an annual basis in accordance with relevant AS. Reports reviewed for any out of parameters levels which require corrective action and the records to be kept on file. Service provider engaged to carry out testing must provide written report which FM is to review for out of parameter levels, addressing corrective action where required. Manufacturers recommendations for safe use of products - Safety Data Sheets (SDS) and equipment to be adhered to for process’s within buildings that may affect air quality i.e. dry cleaning, generators etc. | FM to ensure annual testing of IAQ, or at more frequent intervals if deemed necessary. Monthly testing of water system quality. | M6 | Building Manager, Facility Manager, Service Providers
BIOLOGICAL
Infection control • sharps, syringes etc. | Exposure to blood borne infectious diseases | H16 | Ensure blood/faeces are cleaned up immediately after reporting, ensuring cleaners adherence to their own company procedures for such risks relating to bodily fluids. Ensure reported hypodermic needles, syringes, condoms or other, are collected immediately after they are reported, utilising the recommended containers and tools, ensuring cleaners adherence to their own company procedures for such risks relating to infection control, sharps etc. | Elimination | Maintain staff and tenant awareness of reporting and immediate response procedures to identified blood/ faeces incidents. Manage any potential for exposure to sharps (needles, syringes or other), blood spills or other human tissue/substances to protect personnel from the risk of infection. Cleaning Service Provider adherence to SMP and SOP on procedures for such risks relating to infection control, sharps and the possible exposure to biological risk in the workplace. | Records maintained in iSystain. CM to regularly review cleaning contractor compliance with Service Agreement commercial cleaning and the floor maintenance plan and Safe Operating Procedures (SOP's) or Safe Work Method Statements (SWMS). | L3 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
COMMUNITY CONTACT
Community contact | Adverse media coverage and escalated environmental damage | M10 | All contact from the community including complaints, reports etc. are to be registered in iSystain within 24 hours Members of the community are to be contacted within 24 hours of the complaint received by Building Management. All Building Management Staff to follow Media Relations Policy. Resident contacts to be registered in Salesforce | Administration | Building Management staff to ensure all community contact is reported with corrective action implemented. | Records maintained in iSystain.??? Salesforce | L3 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
CONTACT WITH ELECTRICITY
Electrical tools & equipment | Electrocution or damage to property due to faulty or poorly maintained equipment | H22 | Limitation of domestic tools and equipment (industrially rated leads and plugs); Elevation of leads and protection with plastic stand hooks; Use of rated conduits for temporary wiring; Compliance testing of supply and wiring and leads and RCDs; Power supply (mains or generator) fitted with Residual Current Device (RCD); Service provider - Pre-start check of condition of leads and tools and check within test date; All portable electrical equipment, which includes all equipment and appliances that are connected to the electricity supply [240 – 415v] by a flexible cord, including portable power supplies, extension cord sets and power boards, also fixed and portable Residual Current Devices (RCD) installed and used in accordance to AS/NZS 3760-2010 and AS/NZS 3012-2010. Ensure all electrical equipment is used and maintained as per manufactures recommendations and operational manuals. Lock out/tag out isolation in use for faulty equipment. | Engineering | Performance of RCD tested by qualified electrician on establishment of supply and thereafter at six monthly intervals; Workplace manager to engage licensed electrical contractor to carry out Annual Thermography Scans and testing and tagging as required | Annual RCD test records 6 Monthly RCD push test records Electrical tag and testing records | M10 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Electrical Installation (switch board) Supply (transformer) Working on Switchboards and DB | Electrocution Fire or damage to property due to faulty or poorly maintained equipment Non compliant electrical work Fire or damage to property due to non compliant electrical installation | H22 | Design and plan adequate switch boards to prevent running overlength leads; Design of electrical equipment and switchboards to prevent contact with live parts and adequate IP rating; Residual Current Devices (RCD) installed and used in accordance to AS/NZS 3760-2010 and AS/NZS 3012-2010. Mirvac Thermographics and Isolation procedures to be adhered to. Determine if any onsite transformers are owned by either the electrical authority or Mirvac. Certification of wiring supply (compliant to AS3012). | Elimination | Wokrplace Manager to engage licensed electrical contractor to carry out Annual Thermography Scans and testing and tagging as required. Workplace Manager to place isolation stickers to all boards to remind workers of isolation procedure. Review operation manual provided by the supplier of the transformer to determine inspection and maintenance requirements to ensure safe ongoing operation and engage suitably qualified contractor to undertake the works. | Workplace Manager to obtain Annual Thermoscan Report . Workplace Manager to undertake regular inspection of workplace as per FCR36. Inspection and maintenance regime to be in MEX to ensure necessary inspection and maintenance works are carried out. | M10 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Underground power cables Drilling/Saw cutting into slab with energised in-situ electrical cables | Electrocution Loss of power | H22 | Design the work to avoid existing underground services; Utilise safer diggging method (non-destructive digging), ceramic handled shovels for pot holing; Use of GPR and cable locators to accurately identify existing services; Errection of hard barriers to protect from contact with the service; Use of pot holing to positively identify service routes; DBYD and As Constructed drawings to identify location and age of service; Hold points in the work as per Excavation Piling Boring Trenching Permit; Dedicated safety spotter during the works. No drilling or cutting into slab (> 40mm) with live electrical cables unless appoval has been given by Mirvac Building Management. Slab scans to be completed is approval is given Check at switchboard locations or underside of floors to determine if conduits and / or cables enter / exit the structure / slab etc. Barricading is to be erected around areas to be cut to ensure only those involved have access. The slab must be cut into block sizes that can be lifted by a crane or a lifting device approved by a competent engineer. For any work involving cutting, nailing, coring or drilling where work is within 3m of a known electrical, gas, water or telecommunications service the Coring Chasing Concrete Cutting Permit must be completed. A Permit must also be completed where the depth of the penetration is >40 mm or is determined by risk assessment to require one. | Engineering | Survey of excavation areas including 'As Executed' drawings and Dial Before You Dig (DBYD) 'Potholing' to visually confirm location/depth and mark routes/depth on survey pegs. Issue Mirvac Excavation Permit including up to date drawings In the event of drilling or cutting into a slab that has live electrical cables, once assessed by site electrician and Mirvac Workplace Manager if the area has potential for live cables in that area then a Mirvac Coring permit must be complete, where isolating all power to that area will be ensured. Toolbox talk and consult service providers on procedure and when slabs are energised, communicate at subcontrators meeting. All services must be marked-up using a non-water soluble fluoro marker plus on the site plan before work starts. High voltage cables must also be sign posted with their location. | Records of Survey/Drawings, DBYD, and Drawing Register On-site observation Records of Consultation Coring/Chasing permit Scan record On site observations | H15 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Undertaking Electrical Work on or near energised services (installation, commissioning, maintaining, fault finding, isolating, testing, re-energising) | Electrocution Explosion | H22 | Person not working on 'live' equipment (e.g., Distribution Board or circuit isolated & locked out); Hard barriers to maintain safe approach distances and prevent inadvertent contact; Rated insulation/intrinsically safe tools to protect if contact occurs; Isolation Lockout Tagout MMR and personal locks; Earth leakage protectors and inbuilt fault tripping; Isolation Lockout Tagout Permit; Training and Competency; Emergency Rescue Kits and Standby Person; Electrically rated PPE, mats, gloves, multimeter; Electrical Handpover processes and certificate. | Engineering | Person is licenced electrician using Service Provider Isolation Procedure or trained in Mirvac Isolation Procedure | Record of competency & isolation training provided Physical lock out/isolation system observed in operation Register of lock out/isolation system implementation | H19 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
CONTRACTOR MANAGEMENT
Mirvac Contractors | Injuries to people, damage to property and the environment | H17 | Mirvac Contractor Registration & Qualification Process to be undertaken by contractor. Contractor audit FCR37 to be conducted twice a month. Review SWMS to ensure adequate control are identified in SWMS. Contractor to follow Mirvac HSE Management System | Administration | Contractors to log in/ out of contractor management system (CMS) daily whilst works are being undertaken. FM to review CMS for site access and compliance | Completion of Mirvac General and Site Specific inductions prior to attending site. FCR 37 HSE Observations | M10 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
EMERGENCY PREPAREDNESS
First Aid | Injuries to people, damage to property and the environment, including escalation | M11 | All LIV staff to be First Aid trained via competency based training from a RTO. At first aider to be on shift at all times. First Aid poster to be displayed in all visible locations. First Aid kits located on L5, L39 and in security office | Administration | Site Specific Procedures Manual to be held on site. BM to ensure evacuation plans (with identified “you are here” stickers) are in place and displayed at Mirvac Retail workplaces. | Observe that evacuation plans are in place and displayed in prominent locations. Regular evacuation training is provided to tenant employees including first aid (supplies and training). | L2 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Naturals disasters | Loss of life, property and interruption to business operations Environmental contamination | H22 | Senior management to be involved to review the location (proximity to hazard – flood prone areas/bush fire zones) and type of asset (structure - to determine if the risks to the asset can be eliminated or minimised. Emergency response plans include actions to manage natural disasters Business Continuity Plans adress business interruption | Administration | Where the risk is present as determine by the DA or council requirements , the development of a flood/bushfire management plan linked to the Emergency Response/business continuity plan (BCP) is to completed and implemented (communicated) into the facility overall site specific procedures. | Weather events which have the likelihood to impact the property are to be monitored through local and state media (bureau of Meteorology, News (TV/Radio) stations. | L3 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Evacuation/Bomb Threats | Damage to Property Loss of life | H22 | Evacuation and control procedures documented in Site Emergency response Plan Documents to be held on site by site team. Procedures to be practiced regularly. Document to be reviewed on a regular basis. | Administration | Verification of annual Maintenance requirement – Service Providers to comply with AS1851 (Routine service of fire protection systems and equipment) Emergency Evacuation training for all employees and use of certain fire equipment (QLD/ fire extinguisher). All systems and equipment to be tested as per AS 1851 and certified by contractor allow the Annual Fire Safety Statement to be completed and issued to council, as well as Insurers and National Ops Mgr. advised of impairments and of their return to service. | Fire system inspection and critical dates maintained as per Mex requirements. Annual Emergency Evacuation Drills. Bi- Annual Emergency Control Organisation (ECO) training. | M9 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Fire | Fire, loss of life and property | H15 | All buildings include fire protection systems to detect and prevent the spread of fire. Fire systems to be identified in Emergency & Evacuation Management Plans All isolations of fire systems to be recorded by “Isolation Permit” at Building Management as well as isolation log book at FIP. Impairment notices sent o insurer when impairments as per insurer requirements | Administration | Verification of annual Maintenance requirement – Service Providers to comply with AS1851 (Routine service of fire protection systems and equipment) Emergency Evacuation training for all employees and use of certain fire equipment All systems and equipment to be tested as per AS 1851 and certified by contractor allow the Annual Fire Safety Statement to be completed and issued to council, as well as Insurers Notify insurere as per their requirement | Fire system inspection and critical dates maintained as per Mex requirements. Annual Emergency Evacuation Drills. Bi- Annual Emergency Control Organisation (ECO) training. | L5 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
LIFTS
Lifts | Entrapment, falls from heights, crush injuries | H20 | Lifts operation and maintenance must be in compliance to Lifts Procedure. Regular inspections to be undertaken. | Isolation | Lifts,are to be covered by comprehensive (maintenance) contracts provided by recognised lift maintenance companies. | FM to carry out routine inspections of lifts, travelators and travelators or as per FCR36 requirements. | M9 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
FALLING OBJECTS
Stationary Working Platforms (e.g., scaffolds, elevated walkways, trestles) including collapse | Object falling from height Hit / Strike employee resident or member of public | H16 | Use of physical barriers to prevent objects dropping (containment meshing); Brick guards fitted where potential for falling objects exists; Protection of the structure from being hit by loads or mobile plant; Toe boards installed; Scaffolds, walkways, elevated work areas e.g., slabs, roofs have toe boards installed.; Work within the design rating of the equipment; Management of Change process to ensure integrity is maintained when structure changes; Scaffolding design drawings and plans and checks that construction is compliant. | Isolation | Handover certificate received Mirvac inspection prior to acceptance. | Records of Certificates and Inspections On-site observation | M10 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Mobile Working Platforms (e.g. Elevated Work Platform (EWP), Scissor Lift, Swinging Stages, mobile scaffolds) | Object falling from height Hit / Strike employee resident or member of public | H16 | Staging of the work when no-one else around; Separated work fronts to avoid simultaneous operations Exclusion zone implemented and actively managed Tool lanyards used where risk of dropping Adhere to minimum standards for design compliance Work within the design rating of the equipment; Management of Change process to ensure integrity is maintained when structure changes; OEM requirements complied with; Processes for the management of Design of Temporary Works; Plant Arrival Checklist; Plant Risk Assessment; Work at Heights permits and Plant maintenance and inspection regime; Verification of Competency for operators; High Risk Work Licenses where required (e.g. scissor lift over 11m). | Elimination | Handover certificate received Mirvac inspection prior to acceptance Dynamic Risk Assessment Regular moitoring of contratcor activities Exclusion zone marked and maintained | Records of Certificates and Inspections On-site observation | M10 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Balconies | Object falling from height Hit / Strike employee resident or member of public | H20 | Balaustrades to BCC Requirements for loose objects to be secured or moved away from balaustrades | Administration
KITCHENS
| Exhaust Fan Fire | H16 | Exhaust fans and ducting maintained in accordance with food standard requirements. | Engineering
HAZARDOUS SUBSTANCES & DANGEROUS GOODS
Storage and Handling of Hazardous Substances & Dangerous Goods | Spills or discharge causing contamination of air, water or land Injury/Illness of Member of Public, Resident, Contractor or Worker | M10 | Wherever possible substitute with less hazardous chemicals Substances/goods stored and handled in accordance with SDS (Safety Data Sheet). Appropiate bunding for hazardous chemicals Untrained people not to use or determine storage requirements for hazardous substances or dangerous goods Products stored in approved cabinets or purpose built containment areas Hazardous Substance Risk Assessment completed including research and purchase of less hazardous/ dangerous products All users of hazardous substances appropriately trained and have adequate PPE Spills kits in stock Appropiate First Aid facilities including eye wash stations | Substitute | Products & Hazardous Substances Register completed listed SDS (Safety Data Sheet) for all products in use, issue date less than 5 years old. Hazardous Substance Risk Assessment completed for all products/substances/goods classified as hazardous Products/substances correctly labelled Person trained in storage and use of hazardous substance and dangerous goods as outlined on the HSRA and in the MSDS (SDS) Appropiate number of spill kit and in appropriate locations | Records of MSDS (SDS) Spill Kit stocked and ausited. Records of spill response training available. On-site observation. Drainage outlet to bunding locked. | L5 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
HOT WORK
High risk hot work (welding, burning or angle grinding) - (within occupied building or in a confined space or 15 metres of flammable or explosive material, formwork, reinforcement fixing, completed) | Fire Burns Property damage Environmental damage | H16 | If possible, redesign the work methodology to a non-heat producing methodology; Hot Work Permit used and copy at location of work; Trained and competent operator; Non-flammable sscreens to protect flammable substances from the work; Fire equipment working properly and located within 2 metres of hot work; Spotter in place with fire fighting equipment; Fire Equipment Register and maintenance program If welding/cutting, gas cylinders secured and have flashback arrestors fitted at torch and gas bottle on both hoses; | Engineering | A competent and experienced person has conducted a Risk Assessment of the proposed work and inspected the workplace. Hot Work Permit issued in accordance with the Hot Work Procedure, and discussed with the person undertaking the hot work. Include potential of falling objects and hot material from overhead Hot Works in JSEA Review of Hot Work Permit if work conditions or location changes. Inspection during hot work task. Permit closed out at conclusion of hot work Pre-start check on all equipemnt used for the hot works 12 monthly testing/ replacement of flashback arrestors Flashback arrestors fitted by competent person (e.g. plumber, welder) Inspection of fire equipment carried out within last 6 months Personnel trained in use of fire extinguishers | On-site observation Hot Work Permit at work location, all conditions comply Maintenance records | M10 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
LIGHTING
Lighting (inadequate lighting) | Injuries to people, damage to property | M11 | Building Fit Out specifications for common areas are sufficiently lit. Lighting enables employees,and service providers to carry out work free from risk to health and safety. Apartments are adequately lit Compliance with the relevant Australian Standard for LUX Levels | Engineering | FCR 36 | Regular lighting inspections undertaken with defects identified and reported. Night audits completed | L2 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
MANUAL HANDLING
Any activity which requires the use of force exerted by a person to lift, lower, push, pull, carry or otherwise move, hold or restrain an object, involving repetitive or forceful movements and any activity where a person must maintain a constrained or awkward posture. | Sprains, strains and damage to joints ligaments and muscles | H16 | When designing a work area or workplace or before purchasing equipment, (such as tools, containers, workstations, machinery and vehicles), consideration must be given to safe access and use. Elimination of hazardous manual tasks must be a priority when designing systems of work. Where elimination is not possible, the Hierarchy of Control should be consulted to determine the best way to use substitution, or if not practicable, isolation and engineering controls, prior to relying on administrative controls. Where Service Providers are engaged to perform manual work the Mirvac tendering and Induction/on-boarding process must require Service Provider employees to have undertaken manual handling training / training in the management of hazardous manual tasks. | Elimination | Training in correct manual handling techniques (incl. on-going toolbox talks, coaching) Mechanical aids in use and maintained Bulk loads secured on trolleys to prevent toppling Floors/areas preloaded e.g., plasterboard & fittings, to minimise lifting and double handling | Records of training On-site observation Maintenance records | M10 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
OCCUPATIONAL EXPOSURES
Thermal Stress/ UV radiation | Illness to workers from long terms exposure | H16 | Job rotation, provision of PPE, rest breaks, provision of thermally regulated break rooms Project personnel alerted to substances and risk of exposure; Limit very physical work to early mornings when cooler; Shade and water stations; Stopping work in extremes of temperature; Wearing of protective clothing and hats an use of sunscreed; National HSE Manager trained in Mirvac Occupational Exposures Training; Occupational Exposures covered in Induction Training for all workers | Elimination | Supervision of work design and task rotation; Workplace inspection (ensure adequate shade structures); Thermometers and BOM forecasts; Temperature and Humidity monitoring | On-site observation by Mirvac and regular inspections; | M9 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
VOC's | Illness to workers from long terms exposure | H16 | Hazardous substance pre-purchase risk assessment- low VOC process; Use of forced/ natural ventilation; Respiratory protection; Project personnel alerted to substances and risk of exposure; HSE Manager trained in Mirvac Occupational Exposures Training Occupational Exposures covered in Induction Training for all workers | Substitute | JSEA/SWMS approval process considers required controls Required training occurs; | Site Inspections and Audits; Induction Records | M10 | Workplace Manager, Facility Manager, Building Management Staff, Service Providers
OCCUPATIONAL NOISE
Noise | Damaged to hearing from noise levels above the prescribed limits. Discomfort to the community | M11 | On-site noise monitoring conducted to record noisy activities conducted on site. (Mirvac Occupational Exposures MMR) Noisy activities isolated from general work areas by noise barriers wherever possible Personal hearing protection relative to the recorded noise level is worn, whilst works conducted or as identified within JSEA's Use of noise minimising tools (purchase and use of equipment with dB ALARP) | Engineering | Employees or other workers frequently required to use personal protective equipment to protect against the risk of hearing loss associated with noise that exceeds the exposure standard will be monitored by their employer through audiometric testing. Noise monitor to be calibrated according to manufacturers instructions, and Occupational Noise MMR. Inspection of isolation barriers Noise monitoring included as part of inspection schedule. | Records of Noise Monitoring; Records of Calibration; Records of hearing test programs On-site observations | L2 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
PLANT, EQUIPEMENT & VEHICLES
Operation of Plant in Loading Docks and common areas | Injuries to people Damage to property | H20 | Reducing the number and type of plant at site; Separation of plant interaction with public and workers including use of exclusion zones; Plant arrival checklist to be completed including optaining appropiate licenses, registration, licenses, maintenance history; Plant arrival checklist completd Appropiate permit completed Traffic Management Plan; Rules of operation are established, documented in JSEA/SWMS and enforced (e.g., speed limits, looking in direction of travel, stopping at blind corners); Daily operational and safety checks; Daily pre-starts cover site movements; Plant and vehicles operate as designed - e.g., brakes, visibility, steering, reversing beepers to be used Radios and positive communications and spotters when pedestrian enters plant operating zone; Verification of competency of Plant operators; Visible and trained spotters; Reversing is in place wherever possible; If more than 1 plant, pedestrian follows directions of spotter or stops until safe to proceed; High Visibility clothing | Engineering | Plant inspected on arrival to site Daily pre-start completedInspection and maintenance as per manufacturer's requirements Regulatory Authority Registration current for high risk plant Clear delineation of pedestrians from plant/vehicles exists (e.g., barriers, barricades, handrails). Exclusion zones around operational plant, e.g. mobile cranes, piling rigs, excavator or other If more than 1 plant/vehicle, Traffic Management Plan prepared by competent person (with certificate) Requirement for spotter, PPE and reversing beeper included in JSEA Spotter rotated regularly Operator is licenced | On-site observation Maintenance records available Regular inspections Completion of FCR 36 and 37 Record of competency Permit Plant Arrival Checklist | H15 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Operation of plant and equipment (e.g., blades, chains, rotating parts) | Injuries to people Damage to property | H20 | Selection of tools and machinery that have moving parts covered; Appropriate guarding in place to protect sheaves, blades, moving parts and hot parts; Exclusion zones to separate workers from mooving parts; Interlocks to cut power to moving parts; Routine workplace inspection program checks for guarding and reqiured exclusion zones (FCR 36 & HSE Task Observations); Plant arrival/induction checklist checks for fixed guards in place; registration, licensing, maintenance; Appropiate Plant Permit JSEA/SWMS stipulate required PPE; Operators trained in correct use; All plant and equipment undergoes routine maintenance to OEM requirements; All signage and warning signs in place: decals, crushing hazards, pinch points etc.; Plant Risk Assessment ; PPE. | Engineering | Inspection of guards including adequacy of screening and fixings Pre operation checks and regular inspections. Operator is competent to use equipment. | On-site observation Lockout Tag our Procedure. Maintenance Schedule and Reports. Pre-operational check and inspections. | L5 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Waste Chutes | Waste put into wrong chutes Chutes jammed Prohibited material put into the waste system Injuries from attempting to climb into the chute |  | Chite design |  |  |  |  | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Maintenance of plant and equipment | Injuries to people Damage to property | H16 | No work on equipment that is not isolated, i.e. locked out, or de-energised; Maintenance plan as per OEM requirements; On-line reminder for plant servicing (MEX); Plant and Equipment Register and records; Qualified mechanics performing servicing; OEM Instructions for servicing and maintenance; Plant Risk Assessment. | Administration | 'Test for Dead' before work commences | Records of isolation - lock out/tag out register | M11 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
MARKETING ACTIVATIONS
Marketing Activations | Injuries to people Damage to property | M11 | The stability of any fittings or fixtures; Identifying any protruding sharp edges; Parts of the fixtures which are below the line of sight which may present a trip hazard; All extension leads raised off the floor and secured so as not to obstruct the safe movement of people; Fire exits, the hose reel and fire extinguishers are not obstructed in any way and are maintained; The appropriate clearances still exist for sprinkler heads, smoke detectors or other ceiling related mountings; All electrical appliances are tagged by an electrician and are current for the type of device and its application The Lessee is not overloading the power circuits made available for his or her use (double adaptors and power boards without an Residual Current Device are prohibited) and; Any electricity supply used in business operations is protected. | Administration | Ensure the lessee has appropriate and current Public Liability Insurance. Complete the mkt assessment befiore engagement Complete Pop Up Inspection before trade | Pop up checklist Pop Up Induction requirements Pop Up Procedure | L2 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
PLANT ROOMS
Main Plant Room Sprinkler Valve Room Switch Rooms Lift Motor Rooms Fire Control Rooms | Injuries to people, damage to property | H16 | All plant and switch rooms are to be locked, secure with access keys to be restricted. Unauthorised access into the plant rooms to be prevented. Plant rooms to be free from unnecessary items and must contain sufficient lighting. Plant room to be on the master key system and only issued to Mirvac Inducted Contractors | Elimination | Access control system to be put in place to monitor access. Appropriate signage to be installed at entries. | Regular security checks to be undertaken to ensure enclosures remain locked and secure. Completion of FCR36 inspections | L2 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
SECURITY
Security Operations Resident safety | Injuries to people, damage to property | H20 | Asset Security risk assessment to be facility type / tenant profile to be assessed for heightened threats. Security Operations: Facility type to be consider in the procurement of Security Service Provider. Compliance with Mirvac Service Provider Procedure. Swipe access to CCTV in common area, amenity floors, carpark and main entry points All security guards to participate in Emergency Response training and scenario training "Fulcrum" Training that is undertaken | Administration | Discussions with Security contractor for appropriate controls as per level of threat. Security Operations: Site Specific security procedures for various activities to be in place e.g. patrols, after hours procedure, JSEA for common activities | Maintaining security procedures and business continuity plans. Security Operations: Completion of FCR37 at regular intervals. | M9 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
STORM WATER DISCHARGE
Storm Water Discharge | Environmental Damage | H15 | Ensure that the only connections to stormwater are related to the drainage of rainwater from hard surfaces Ensure that areas draining to the stormwater system are maintained and free from litter and debris. Ensure that waste containers are provided in appropriate areas to prevent litter entering the stormwater system Ensure that all chemicals stored near stormwater drains are bunded to prevent leaks and spills from entering the stormwater system. | Engineering | Provide a spill kit where appropriate, for example in loading dock, to ensure that oils, fuels and chemicals do not enter the stormwater system. | FCR01 FCR036 Daily Operational Inspection | M9 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
TRAFFIC MANAGEMENT
Car parks Loading docks Pedestrian Management | Vehicular collision, people struck by moving objects, crush injuries and damage to property | H17 | Loading Docks to be designed and operated to effectively separate pedestrian and vehicles. Where pedestrians and plant/vehicle can be separated- Pedestrians separated from moving plant/vehicles. Mirvac JSEA/RA for loading docks to be implemented into all Mirvac managed locations identified with such an area Where pedestrians and plant/vehicle cannot be separated- High visibility vests, reversing alarms and flashing beacons/Pedestrian makes eye contact with plant operator before approaching. Where possible to ensure there are designated pedestrian paths and crossings Loading Dock Management Plan to be in place including pedestrian / vehicle interaction Carpark rules are established and displayed (e.g., speed limits,stopping at blind corners, directional signage and line parking & speedhumps) | Isolation | Where pedestrians and plant/vehicle can be separated- On-site observation/ Record of TMP and certificate of competency. Where pedestrians and plant/vehicle cannot be separated - On-site observation/ Record of competency. Issues and safety concerns to be raised and discussed at the tenant / retailer meetings | Regular inspections undertaken using the MEX system of reporting and defect identification. Appropriate signage / line marking/ barricades to be in place. | L5 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
WORK IN CONFINED SPACES
Entry into confined space • Grease traps • Pits (Lifts) • Storage & Retention Tanks • Cooling towers • Drainage pits | Entry by unauthorised person | H20 | Design out confined spaces if possible; Confined space identification carried out by person trained in confined spaces (by RTO with confined spaces in their scope). Register of Identified Confined Spaces maintained . Confined space entry permit completed by person trained in confined spaces (by RTO with confined spaces in their scope). Standby person at confined space entry point controls entry and exit. Personnel that enter confined space and standby person are confined space trained (by RTO with confined spaces in their scope). Gas monitor has a current calibration, and is 'bump tested' in fresh air prior to each use. Emergency retrieval system has been prepared or authorised by a person that is confined space trained (by RTO with confined spaces in their scope). Davits, harnesses, SCBA, Gas monitors, Rescue sets (PPE); | Isolation | Confined space identification carried out by person trained in confined spaces (by RTO with confined spaces in their scope) Register of Identified Confined Spaces maintained Confined space entry permit completed by person trained in confined spaces (by RTO with confined spaces in their scope) Person that accepts risk assessment is trained in risk assessment Standby person at confined space entry point controls entry and exit Personnel that enter confined space and standby person are confined space trained (by RTO with confined spaces in their scope) Gas monitor has a current calibration, and is 'bump tested' in fresh air prior to each use. Emergency retrieval system has been prepared or authorised by a person that is confined space trained (by RTO with confined spaces in their scope). | Register of Identified Confined Spaces Record of training Records of D.O.O.R processes Record of training Record of Risk Assessment On-site observation Register of persons entry/exit to space Record of calibration and 'bump tests' Register of persons entry/exit to space. Records of evacuations and training drills. | H15 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
WORK AT HEIGHT
Other Work at Heights | Falls from a height | H20 | For all tasks 2.0 metres and over, identified as having potential for persons to fall. Risk Assessment to identify the most appropriate fall prevention method for the location specific task, including 'fall restraint' & 'travel restraint' utilising the Hierarchy of Control. Emergency Rescue Plan (ERP) incorporating a Retrieval Plan developed | Administration | Task personnel are involved and trained in the location/task specific JSEA (or equivalent) & ERP; Task personnel have attended recognised Fall Equipment training to "Work Safely at Height" Include potential of falling objects and hot material from overhead Hot Works in JSEA Correct installation & use of appropriate fall arrest equipment identified above | JSEA (or equivalent) & ERP with Retrieval Plan for specific task/location Statement of Attainment - Work Safely at Height Task personnel have Statement of Attainment - Work Safely at Height | H15 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Façade access (cleaning, inspection, maintenance) • Internal / external glass cleaning (EWP- see falling objects) • Industrial rope access No BMU onsite | Falls from height/ falling objects | H20 | Engage appropriately qualified Industrial Rope Access (IRA) consultant to carry out cleaning & inspections of internal/external facades. If access to edge of roof is required (less than 2 meters) fall arresst is required. Fall arresst to be tested and in date All roof access to be controlled therough a master key. Roof access permit, Rope access permits, IIP Work at heights Dynamic Risk Assessment All davit arms and anchor points maintained and certified Emergency rescue plans | Administration | Service Provider to undertake CMS process Roof access permit, Rope access permits, IIP Work at heights Dynamic Risk Assessment Roof Access Management Plan to be adhered to JSEA (or equivalent) signed by work crew, for all external tasks to establish effective means of preventing falling objects, and preventing injury to personnel. Certified anchor point(s), safety lines and davit arms/jockeys | Routinely check roof access during property inspections. On-site observation. oof access permit, Rope access permits, IIP Work at heights Dynamic Risk Assessment Fall restraint equipment register. Record of inspection by a competent person at maximum 6 month intervals for safety harness and max 3 months for wire ropes or other fall arrest equipment. Anchor point(s) , safety lines and davit arms/jockeys certified prior to use or at max. 12 month intervals. Training in the use of fall arrest equipment verified | M9 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Roof Access | Falls from height/ falling objects | H20 | No work with 2 metres of the edge for flat roofs less than 5 degrees. If access to edge of roof is required (less than 2 meters) fall arresst is required. Fall arrest equipment to be tested and in date All roof access to be controlled therough a master key. Roof access permit. Dynamic Risk Assessment for work at heights on external of asset eg rope access activities | Administration | Fall prevention strategy determined. Scaffold or guardrail or other edge barrier provided. Fall restraint system for flat roofs for work within 2 metres of the edge where the potential fall height is 2 metres or more. Safety mesh installed below roof sheet. | Handover certificate for scaffold or guardrail. Records of inspection at max. 30 day intervals. On-site observation. Roof Access permit for roofs in excess of 2 storeys. Fall restraint equipment register. Record of inspection by a competent person at maximum 6 month intervals for safety harness and max 3 months for wire ropes or other fall arrest equipment. Anchor point(s) certified prior to use or at max. 12 month intervals. Training in the use of fall arrest equipment verified. | M9 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
Ladders | Falls from height/ falling objects | H16 | Platform ladders are to be used. If a platform ladder can not be used a risk assessment is to be completed. All ladders to have an annual inspection and have a Mirvac compliance sticker Restricted use of ladders, especially near open penetrations, edges, stairs or balconies No climbing above 3rd highest rung, use 3 points of contact and chest to remain within stiles of ladder | Engineering | Visual inspection of ladders Ladder rated for industrial use (120 kg max), minimum 1.2 metres and in good condition. No climbing above 3rd highest rung, use 3 points of contact and chest to remain within stiles of ladder Where repeated access to heights of 2 metres or more is required, an elevated work platform, (e.g. mobile scaffold or other) is used instead of a ladder, or handrail erected where ladder near an edge | "Inspection before each use" included as Control Measure in JSEA for task Included in Induction topics On-site observation | M10 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
VISITORS
Visitors | Injuries to visitors | H20 | Resident visitors to be escorted by resident when on amenties and wellness floors. Mirvac visitors to be escorted while on the premises unless inducted Relevant safety concerns and issues to be advised to visitors by escorting agent. NB: Mirvac Visitors who frequent(more than once) site must be inducted. | Engineering | All visitors to sign in using Mirvac CMS when entering and exiting the premises. | FM and HSE to regularly review CMS for compliance. | M6 | Wokrplace Manager, Facility Manager, Building Management Staff, Service Providers
ENVIRONMENTAL ASPECTS
AIR QUALITY
Indoor and outdoor air quality | Adverse reactions by tenant, public and employees to chemicals, particles and/or substances in the air | H16 | Minimise dust released by disturbance of soil and/or gaseous emissions from operation of plant and equipment or vehicles. Provide clean, healthy, fresh air to facility at all times. Ensure adequate ventilation. Ensure recommended chemicals and treatments are used in the correct quantities at all times. | Engineering | Testing for bacteria, CO’s, temp and humidity on an annual basis in accordance with relevant AS. Reports reviewed for any out of parameters levels which require corrective action and the records to be kept on file. Service provider engaged to carry out testing must provide written report which FM is to review for out of parameter levels, addressing corrective action where required. Manufacturers recommendations for safe use of products - Safety Data Sheets (SDS) and equipment to be adhered to for process’s within buildings that may affect air quality i.e. dry cleaning, generators etc. Plant inspected on arrival to site. Daily pre-start completed. Inspection and maintenance as per manufacturer's requirements. Minimise stockpile heights. Stabilise long term stockpiles e.g. grass/ hyrdomulch | FM to ensure annual testing of IAQ, or at more frequent intervals if deemed necessary. Monthly testing of water system quality. Water treatment service Provider to be regularly monitored to ensure the Cooling Tower Manual compliance is maintained and completed as required. On-site observation Maintenance records available | M10 | Workplace Manager, Facility Manager, Building Management Staff, Service Providers
FLORA AND FAUNA
N/A
HERITAGE
N/A
RESOURCE MANAGEMENT
Potable Water | Depletion of non-renewable resources | M11 | Identify opportunities to reduce potable water consumption in facilities where Mirvac Facility Management have operational control. Deliver on the Mirvac 'This Changes Everything' strategy with respect to potable water intensity. 1. Efficiency - improving water efficiency at our assets (where we have operational control), using the recognised National Australian Built Environment Rating System (NABERs) Water ratings. 2. Offsets - using captured and recycled water at our masterplanned communities’ projects where drinking water can be replaced (for example, toilet flushing and irrigation) to offset drinking water demand. 3. Influence - leveraging our materials and electricity procurement volumes and choices to influence/achieve water savings. | Administration | Monitor and report on building potable water consumption. Perform annual NABERS Water ratings to benchmark performance. Investigate new water efficiency technologies. | Monitor building daily usage profiles generated from smart meter data. Perform a comparison review of monthly water consumption generated from smart meter data. Review historical quarterly water consumption data from invoices and meter data. Review and analyse annual NGERS data. | L3 | Workplace Manager, Facility Manager, Building Management Staff, Service Providers
Energy | Depletion of non-renewable resources Emissions of Greenhouse Gases | M11 | Identify opportunities to reduce energy consumption and Greenhouse emissions in facilities where Mirvac Facility Management have operational control. Deliver on the Mirvac 'This Changes Everything' strategy with respect tocarbon intensity | Administration | Monitor and report on building energy consumption and Greenhouse emissions. Perform annual NABERS Energy ratings to benchmark performance. Investigate new energy and carbon efficiency technologies. | Monitor building daily usage profiles generated from smart meter data. Perform a comparison review of monthly energy consumption generated from smart meter data. Review historical quarterly energy consumption data from invoices and meter data. Review and analyse annual NGERS data. | L3 | Workplace Manager, Facility Manager, Building Management Staff, Service Providers
Materials of construction | Climate change impact at asset | H18 | Sourcing lower carbon materials. buy 25% recycled content in major materials by 2030 increase recycled content in the materials you buy; increase recycled content in the materials you buy; report water leaks straight away to the Tenant Liaison Centr | Engineering | embedded sustainability criteria into our tendering process, design out fossil fuels (commercial/residential); ensuring that our partner businesses understand and support our objectives. extend materials life by selling what’s valuable; recycle;e. | Monitor and report on embedded carbon. benchmark performance.
SPILLS OR DISCHARGE CAUSING CONTAMINATION
Storage and Handling of Hazardous Substances and/or Dangerous Goods | Spills or discharge causing contamination Injury/Illness of Member of Public, Contractor or Worker | H17 | Substances/goods stored in accordance with MSDS (SDS). Storage area bunded and away from drainage inlets or other sensitive areas. Substances/goods stored and handled in accordance with MSDS (SDS). Appropriate PPE made available. Users trained in correct use of substance. | Engineering | Signage and emergency response equipment available relevant to the class of substance/good stored. Nominated personnel trained in spill response. Bunding designed to meet required 110% of largest individual container. No fuel storage within 50 metres of a water body. Spill Kit available. Minor quantities only stored which do not require licencing. Pressurised gas cylinders/bottles secured from toppling and stored in ventilated area | Spill Kit stocked Records of spill response training available On-site observation Drainage outlet to bunding locked | M10 | Workplace Manager, Facility Manager, Building Management Staff, Service Providers
WASTE
Recycles • general and prescribed waste (solid & liquid) | Non-compliance and breaches of EPA regulations | H16 | Waste is minimised & stored securely Waste generated is collected and recycled in accordance to the Waste Management Hierarchy. Waste is managed and stored securely. Waste material is disposed of by reputable contractors in accordance with legislative requirements. Deliver on the Mirvac 'This Changes Everything' strategy | Engineering | Waste storage facilities established according to estimated volume including paint tanks and recycling bins/skips for all streams. Waste sorted on site or at the waste depot. Transporter and receiver of waste are EPA Licensed. Waste transport certificate is obtained (this verifies waste was disposed of in the correct facility) e.g., Adhesives (excluding solid inert polymeric materials), Lime sludges or slurries, Paint sludges and residues, Pesticides (including herbicides & fungicides), Timber preservative residues. Mirvac require waste contractors to only utilise appropriately licenced facilities and to declare these facilities to Mirvac with the licencing details. Mirvac investigate and implement applicable waste management and recycling technologies. Waste Management Plans for each asset where Mirvac Retail manage waste services. Perform waste audits to identify waste minimisation and recycling opportunities. | Monthly waste records including quantities diverted from landfill to recycling Records of licences. Review of service provider JSEA for works which constitute a “material risk to environment/ generate significant wastes streams” prior to commencement of work. Records of certificates of disposal from waste removal contractor which are forwarded to the Sustainability data collection point. Hold regular meetings with waste contractors. Review historical quarterly water consumption data from invoices and meter data. Review and analyse annual NGERS data. | L5 | Workplace Manager, Facility Manager, Building Management Staff, Service Providers
Waste chutes | Chutes blocked by oversized waste putting pets/small child down, jamming fingers, fire, clogged up Fire in chute due to inappropriate wastes being disposed Containation of recyling by putrescent waste | H18 | Signage on each floor on correct usage of of Waste Chutes Area in Basement for placement of oversized wastes for disposal Concealed behind door, Mechanical operation and wait for it to unlock and slow closure mechanism correct usage signs, CCTV coverage outside chute cupboards, | Administrative | Maintain staff and resident awareness of reporting and immediate response procedures to identified waste/chute incidents. Cleaning Service Provider adherence to SMP and SOP on procedures for such risks relating to inappropriate wastes | what monitoring is there on the waste chutes | M10
OTHER
Uncontrolled pets | Urinating/defecating in building Biting resident Fighting other pets | M11 | Onsite cleaners on regular rotation and on call if required CCTV All pets to be on leash when moving through building | Administrative | Maintain staff and resident awareness of reporting and immediate response procedures to incident involving pets Cleaning Service Provider adherence to SMP and SOP on procedures for such risks relating to pets | Cleaning rotations Daily Operational Inspection | M6
Amenity floor | Slips, trips & falls Injury from misuse of gym equipment | M11 | Gym Rules Onsite cleaners on regular rotation and on call if required Equipment Instructions provided for gym equipment Waivers for use of gym amd amenities | Administrative | Maintain staff and resident awareness of reporting and immediate response procedures to identified waste/chute incidents. Cleaning Service Provider adherence to SMP and SOP on procedures for such risks relating to inappropriate wastes | Cleaning rotations Daily Operational Inspection | M6
Residents -self harm | Resident fatality | H15 | SOP for undertaking welfare checks Door reads to monitor movement when there are concerns regarding a particular resident | Administrative | Maintain staff and resident awareness of reporting concerns with any residient, Knowing our residents | regular team discussion to highlight any concerns regardsing residents | M (9)
Dealing with disgruntled tenants or public | Verbal or Physical abuse | H15 | Site staff to work in pairs as buddy system to provide each other personal support Training in dealing with difficult people Never meet in residents apartment, all meeting in team office of lobby | Administrative | Through site team toolbox talk SOP developed to support this | SOP developed to support this | M11 | Workplace Manager, Faciliaty Manager, Tenant Coordination Manager, Centre Management Staff, Service Providers

## MAJOR HSE RISKS
Asstet Name: LIV Munro
Date: 31/07/2024
Prepared By: Site Team
Note: Insert the top 5 HSE risks for your Asset and or any unusual HSE risk
Risk Hierarchy: E = Extreme, H = High, M = Medium, L = Low
Description Provide a description of the identified task or operation | Upcoming, active or closed | Hazard/Risk | Untreated Risk | Risk Mitigation Strategy Provide a summary of the risk mitigation strategy action | Monitoring Activities Provide a summary of how the risk mitigation strategy action will be monitored | Residual Risk | Person / Team Member to Monitor | Changes/ Reviews | Comments Provide any other general comments as required
Window Cleaning | Active | Fall from heights | H16 | Exclsussion zones to be increased to consier falling items from BMU or Rope access. Implementaion of new Miravc Rope access requirements June 22 | Implementation of new Mirvac Rope access policy. | M10 | Workplace Manager, Faciliaty Manager, Tenant Coordination Manager, Service Providers |  | Pre works meeting to commence each day for each service. All permits and exclussion zones to be reviwed by Mirvac management and updated in Rapid
Dealing with disgruntled tenants or public | Active | Verbal or Physical abuse | H16 | Site staff to work in pairs as buddy system to provide each other personal support | Thorough site team toolbox talk | M10 | Workplace Manager, Faciliaty Manager, Tenant Coordination Manager, Service Providers |  | SOP developed to support this
Operation of Plant in Loading Docks and common areas | Active | Injuries to people damage to property | H20 | Traffic mangement plans, agredd procesee with Hotel and Body Corp | Secure high risk plant and equipment to only be operable by site team or contractors. Monitor areas with CCTV | H15 | Workplace Manager, Faciliaty Manager, Tenant Coordination Manager, Service Providers
Electrical works | Closed | electrocution | H22 | use of quialified electricans, no work on live equipment | FRCR37, contrarctor management, daily site walks | H19 | Workplace Manager, Faciliaty Manager, Tenant Coordination Manager, Service Providers
Entry into confined spaces | Closed | Entry by unauthorised person | H20 | All CS have signage and are locked | FRCR37, contrarctor management |  | Workplace Manager, Faciliaty Manager, Tenant Coordination Manager, Service Providers
Major HSE Risks from the Risk Register

## Typical Hazards & Aspects
Typical Significant BTR Hazards & Aspects Checklist
CONTACT WITH ELECTRICITY - Any contact with electricity by person or by plant /vehicle leading to potential electric shock to a person. | HOT WORK - Any Flame or Spark producing activity - welding, gas-cutting, grinding which may cause fire or injury. |  | EFFECTS ON COMMUNITY - Any activities that may lead to actual or percieved degradation of the local community environment e.g. heavy traffic, parking, noise or negative interaction with project personnel.
FALLING OBJECTS - Potential for objects, tools, materials to fall to levels below and cause injury or damage. | MANUAL HANDLING - Stress to muscles from repetitive movements, sudden loading, incorrect lifting, handling techniques or overloading. |  | DISTURBANCE TO FLORA & FAUNA - Disruption, damage or injury to animals, their habitat or local trees, vegetation and plants.
MOVING PLANT/ VEHICLES - Potential collision between items of moving plant/ machinery, or vehicles or contact with persons | CABLES UNDER TENSION - Pre & Post Stressing of concrete. Come-along or chain-block use, hoists and slings. |  | VIBRATION - Vibration from activities that may have a physical effect on the surrounding environment.
MOVING PARTS & STORED ENERGY - Person hit by suspended / flying object, contact with or entanglement in moving parts. | STRUCTURAL FAILURE - Falsework, Formwork & Masonry walls. Collapse or loss of the load-carrying capacity of a component or the structure itself. | SOIL EROSION & SURFACE RUN-OFF - Loss of ground material due to wind/ water action, causing potential siltation/ pollution of waterways. | ENDANGERED SPECIES - Incorrect management, habitat control & identification of endangered species in the local environment.
SUBSTANCES INCLUDING CHEMICALS, GASES & DANGEROUS GOODS - Potential contact to eyes, skin or lungs with Hazardous Substances or Dangerous Goods. | EXCAVATION/ PILING/ BORING/ TRENCHING - Fall of material causing engulfment, persons falling, plant overturning, flooding, contact with underground services. | CONTAMINATED / ACID SULFATE SOIL - Incorrect management/ identification of contaminated or ASS soils. | HERITAGE ISSUES - Incorrect management, consultation or identification of local cultural or heritage issues.
HAZARDOUS MATERIALS - Asbestos, Lead, Polychlorinated Biphenyls (PCBs), synthetic mineral fibres or other as identified causing significant illness. | WORK IN CONFINED SPACES - Areas identified as having potential atmospheric contamination, lack or excess of oxygen or engulfment by free-flowing solids or liquids. | SPILLS OR DISCHARGE CAUSING CONTAMINATION - Discharge & transfer of fuels/oils (hydrocarbons), hazardous substances, dangerous goods, concrete truck wash-out. | DEVELOPMENT APPLICATION REQUIREMENTS - Failure to properly evaluate and implement critical controls may lead to environmental harm, non-conformance, fines and damage to Mirvac reputation.
OCCUPATIONAL NOISE - Workplace noise levels from activities, plant or equipment which has the potential to cause hearing damage to persons in the vicinity. | WORK AT HEIGHT - Potential for persons to fall from an elevated postion and sustain a significant injury. | AIR QUALITY - Potential for pollution by dust, from wind action, disturbance of soil by vehicle/ plant movements. Exhaust emissions from plant/vehicles.
PROJECTILE FIRING TOOLS - Hilti or Ramset explosive charge tools and air or gas powered Nail guns. | WORK OVER OR NEAR WATER - Potential for persons/ plant to slip/ fall into water and risk of drowning. | WASTE - Incorrect management of solid/ liquid waste streams leading to contamination of the environment e.g. bulk earthworks, dewatering, concrete & paint.